JAMM PX

Summer Build Plan

June — August 15, 2026

Confidential — Andrew & Ben

Launch date: August 15, 2026. Everything in this document serves that date.

# 01 — What Changed and Why This Plan Exists

JAMM PX launched its build as a practice management platform competing on consolidation and flat pricing. That positioning was reasonable with the information available at the time. It is no longer the right frame.

A strategy session in late May 2026 produced a fundamental reframe. JAMM PX is a firm intelligence platform. The workflow layer — clients, engagements, tasks, documents, invoices, automations, the portal — is the data collection mechanism. The intelligence layer is the product. The workflow gets firms in. The intelligence makes them impossible to leave.

Every decision in this build plan flows from that reframe. Features that feed the intelligence layer are prioritized. Features that are workflow-only but genuinely useful are included but sequenced after the intelligence foundation. Features that are neither are cut or deferred.

The summer has one job. Make the first ninety days after launch undeniable.

# 02 — What Is Already Built

The codebase is more complete than it might feel right now. A full audit against the roadmap shows the following is production-ready or backend-complete.

## Fully Built and Working

- Complete client management — profiles, contacts, entity types, QBO sync, health indicators

- Full engagement lifecycle — 17 IRS form types, auto-set filing deadlines, status tracking, QC checklists

- Task system — dual-keyed to client and engagement, assignments, due dates, status

- Document requests — checklist templates, portal upload, reminders, completion tracking

- E-signatures via Dropbox Sign — envelope creation, signing flow, webhook handling

- Client portal — magic link auth, todo tab, documents tab, invoices tab, messaging

- Invoicing — creation, sending, Stripe Connect payment flow, webhook confirmation

- Time tracking — entries linked to engagements, billable flag, WIP report

- Automation rules — 13 presets, toggle UI, simulator endpoint

- IRS authorizations — 8821 and 2848 tracking, expiry alerts, authorization badge

- Extension filing — 4868, 7004, 8868, auto-updates deadline

- Tax organizers — three templates, portal section-by-section form

- Transcript requests — workflow, active authorization check

- Firm chat — channels, messages, mentions, file attachments

- Notes system — floating panel, entity-scoped, private notes

- Dashboard — 7 metrics endpoint, stat cards, upcoming deadlines, overdue list

- Calendar — 6-month deadline view, month grid and list view

- Behavioral event log — table, schema, indexes, log_event utility, firing in 35+ places

- TOTP two-factor authentication

- Rate limiting on auth endpoints

- Security headers middleware

- NPS and review request flow — backend complete

- Engagement templates — save, clone, apply

- Concierge onboarding agent — backend pre-build complete, Ben building Phase 2 of 6

## Backend Complete — Frontend Pending

- Automation rule simulator — POST /automation-rules/{id}/simulate exists, no UI

- IRS transcript request — backend complete, frontend panel pending

- Tax organizer in portal — backend complete, portal UI pending

- NPS settings page — backend complete, settings UI pending

- Full firm data export — needs verification and frontend button

## Known Gaps Requiring Immediate Attention Before Launch

- Mock data files still present in frontend/src/lib/mock/ — invoices, tasks, engagements, dashboard reading from local arrays not live API — PRE-LAUNCH BLOCKER

- Staff JWT refresh tokens — identified in previous session as missing

- CORS production configuration — must be locked to specific origins

- Dropbox Sign production API key — sandbox key may still be in production config

- Stripe ca_placeholder — must be replaced with real Connect client ID

- Behavioral event log verification — confirm events actually firing in production for minimum viable event types

- AWS SES domain verification — confirm status or confirm Postmark is handling all email

# 03 — What Is Cut or Deferred

The reframe and the new all-inclusive pricing model eliminate the upsell structure entirely. Everything becomes core product. But not everything needs to be built before August 15th. The following are cut from the summer scope or deferred to post-launch.

## Cut Entirely — No Longer Relevant

- Ring One and Ring Two offer structure — replaced by single tier pricing

- Competition leaderboard for Ring Two — no longer part of the offer

- Async prompt Google Forms system — agent conversations replace this

- Separate index upsell pricing — index is core product, included in subscription

- Client experience pack upsell — white label included in base subscription

- Feature bypass tiers — no tiers exist anymore

- Freemium or lite tier — confirmed not building

## Deferred to Post-Launch — Not Needed August 15th

- Gmail and Outlook integration — significant build, schedule for September

- Client communication drafter agent — depends on email integration

- Custom portal domain per firm — month two post-launch

- Xero integration — non-US market, not relevant at launch

- SOC 2 Type II — needed for enterprise firms above 20 staff, Q4 2026

- Client portal native mobile app — PWA is the interim solution, 2027

- Webhook sender for Zapier — useful but not core, Q3 2026

- File watcher agent for tax software — requires local install, complex support, post-launch

- Budget variance alert automation — QBO feature, post-launch

- Firm health dashboard widget — nice to have, post-launch

- Overdue heatmap — analytics feature, post-launch

- Password policy configuration — IRS 4557 add-on, Q3

- Session timeout configuration — Q3

- Failed login alert — Q3

- Engagement template import from CSV — Q3

- Financial Cents and Karbon migration imports — after TaxDome import works

# 04 — Month One: Foundation First

June 1 through June 30. This month is entirely infrastructure and data integrity. Nothing visible to a firm owner gets built until the foundation is correct. Ben is finishing the concierge agent. Andrew handles everything else.

The behavioral event log must be firing correctly and comprehensively before any intelligence layer features get built on top of it. Dirty foundation equals dirty intelligence forever.

## Critical Fixes — Week One — Andrew

These are blockers. Nothing else starts until these are confirmed resolved.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Remove all mock data files | Delete frontend/src/lib/mock/ entirely. Wire every page to live API. Dashboard, invoices, tasks, engagements all reading real data. | 2 days |
|  | Behavioral event log audit | Confirm with Ben that events are firing in production for minimum viable types. Check engagement.created, invoice.paid, portal.first_login, task.completed, document_request.completed. | Half day |
|  | Staff JWT refresh tokens | Confirm status. If missing, implement. Staff cannot be logged out mid-session on day one. | Half day to 1 day |
|  | CORS production config | Lock to app.jammpx.com and jammpx.com only. Development config is permissive and must not ship. | 2 hours |
|  | Dropbox Sign production key | Replace sandbox key with production API key in droplet config. | 1 hour |
|  | Stripe ca_placeholder | Replace with real Stripe Connect client ID. Billing is broken until this is done. | 1 hour |

## Behavioral Event Log Expansion — Week One and Two — Andrew

The existing log_event utility fires in 35+ places but only captures the minimum viable events. The full tracking schema document identifies hundreds of additional signals. This is the most important build of the entire summer. Add every missing event type before any firm joins.

Critical addition: the log_event function currently checks index_consent and returns early if the firm has not consented. Under the new all-inclusive model every firm contributes data automatically. Remove the consent gate or change it to default true for all new firms.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Remove index_consent gate from log_event | Every firm contributes data by default under new pricing model. The consent check must be removed or defaulted to true. | 2 hours |
|  | Add missing engagement events | engagement.deadline_changed, engagement.reopened, engagement.archived, revision cycle tracking, scope creep signal, complexity flag logging on each engagement. | 1 day |
|  | Add missing document events | document.viewed, document.downloaded, document.deleted, failed upload attempts, upload sequence pattern per client. | Half day |
|  | Add missing invoice events | invoice.viewed, invoice.adjusted_downward, late_fee.assessed, late_fee.waived, payment_plan.created, write_off.recorded. | Half day |
|  | Add missing portal events | portal.session_depth, portal.page_sequence within session, device type on every portal interaction, time of day patterns. | Half day |
|  | Add missing staff events | time_entry.lag calculation, staff.complexity_tier per assignment, feature.opened_and_abandoned, session.abandonment with flow position. | 1 day |
|  | Add missing firm events | firm.feature_adoption_sequence, automation.override, template.modification_delta, settings.change. | Half day |
|  | Add referral source field to client creation | Structured dropdown on new client form. Referring client ID field if referral source is existing client. Both feed referral intelligence layer. | Half day |
|  | Add staff skill set tags | Multi-select field on staff profile for engagement types they are qualified to handle. Foundation for engagement type distribution intelligence. | Half day |
|  | Add staff hourly cost field | Loaded hourly cost per staff member in firm settings. Required for profitability calculations. | 2 hours |
|  | Add firm location zip code | Precise location field on firm setup. Required for geographic clustering and external event correlation. | 1 hour |

## Fee Schedule with Complexity Modifiers — Week Two — Andrew

This is the day one pricing intelligence feature. Firms enter their base fee per engagement type plus modifier amounts for complexity flags. The intelligence layer immediately shows the gap between what they charge and what the complexity suggests they should charge.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Fee schedule backend model | FeeSchedule model per firm. Base fee per engagement type. Modifier amounts per complexity flag. GET and PATCH endpoints. | 1 day |
|  | Fee schedule frontend UI | Settings tab for fee schedule. Engagement type list with base fee input. Complexity modifier section per type. Clean form that a non-technical firm owner can fill in. | 1 day |
|  | Pricing gap calculation endpoint | GET /intelligence/pricing-gaps. Compares actual billed amounts from time_entries against fee schedule plus complexity flags present. Returns list of engagements where firm is undercharging and by how much. | 1 day |

## Ben — Concierge Agent — All of Month One

Ben stays focused on completing the concierge agent through month one. He is on phase 2 of 6. The agent needs to be complete and tested before it can transition into the persistent assistant role it will hold post-onboarding. This is his entire month one.

Specific requirement to flag to Ben: the agent conversation logging must feed the behavioral event log. Every question a firm asks the agent, every topic they need help with, is a product intelligence signal. Make sure the concierge conversation events are wired into the event log from day one.

# 05 — Month Two: Intelligence Layer

July 1 through July 31. The foundation is solid. The event log is comprehensive. Now build the features that make the intelligence visible to firm owners. This is what makes the product categorically different from anything else in this market.

## Morning Briefing — Andrew — First Two Weeks of July

The single most important frontend feature in the entire product. Replaces the current dashboard with an opinionated daily situation report. Three to five things that actually matter today, sequenced by real urgency, written in plain language.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Morning briefing backend endpoint | GET /intelligence/briefing. Reads current state across all domains simultaneously. Surfaces top items by urgency score. Returns structured list with item type, entity reference, urgency level, plain language description, and recommended action. | 2 days |
|  | Urgency scoring logic | Algorithm that weights deadline proximity, financial risk, client health signals, staff workload, and historical patterns. Items sorted by composite urgency score not by category. | 1 day |
|  | Morning briefing frontend | Replace dashboard hero section with briefing surface. Not widgets. One synthesized view. Plain language items. Each item links to the relevant entity. Acted on versus dismissed tracking per item. | 2 days |
|  | Briefing interaction tracking | Log every briefing item that gets clicked versus dismissed and how quickly. This is the accuracy feedback loop for the intelligence layer. | Half day |

## Pricing Intelligence UI — Andrew — Week Two July

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Pricing gap dashboard surface | Surface the pricing gap calculation on the dashboard and on individual client profiles. Show total annual undercharging across all clients. Show per-client gap. Show which complexity flags are driving the gap. | 1 day |
|  | Fee schedule completion prompt | If a firm has not filled in their fee schedule, surface a prompt in the morning briefing and on the pricing gap section explaining what they are missing and why it matters. | Half day |

## Client Intelligence Layer — Andrew — Week Two and Three July

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Client profitability calculation | GET /intelligence/client-profitability. Revenue per client minus staff cost based on hours logged and loaded hourly rate. Sort by margin. Show which clients are actually profitable versus which are consuming margin. | 1 day |
|  | Client profitability surface | Add profitability indicator to client list and client detail page. Visible to firm owner and manager only. Color coded. Shows revenue, cost, margin, and effective hourly rate. | 1 day |
|  | Churn prediction signals | Flag clients showing behavioral warning signs. Response time increasing over 60 days, portal logins declining, engagement count declining year over year. Surface in client health indicator and morning briefing. | 1 day |
|  | Client satisfaction pulse | Single question sent after engagement completion. One to five scale. Auto-sent via Postmark. Response logged in behavioral event. NPS backend already built — wire it to this flow. | Half day |

## Growth Intelligence — Andrew — Week Three July

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Capacity projection endpoint | GET /intelligence/capacity. Based on current engagement pipeline, historical completion rates per staff member per engagement type, and staff available hours. Returns whether firm has capacity for new clients before next deadline cluster and how many. | 1 day |
|  | Growth readiness surface | Dashboard widget showing current revenue per staff member against industry benchmark. Projected revenue at current growth rate. The specific revenue threshold where adding a staff member becomes financially justified based on loaded cost versus additional capacity. | 1 day |
|  | Pricing drift detection | Flag fee schedule amounts unchanged for over 12 months. Flag clients where complexity has grown but fees have not. Surface in morning briefing and in client profile. | Half day |

## Industry Benchmark Foundation — Andrew — Week Four July

Before the network has enough firms for peer benchmarks, industry data serves as the comparison point. Research and hard-code the benchmark values from AICPA PCPS survey, state CPA society reports, and practice management publications. Label clearly as industry-sourced.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Industry benchmark data research | Find specific published numbers for: document collection speed average days, invoice payment time average days, portal adoption rate percentage, engagement velocity by form type, deadline adherence rate. AICPA PCPS benchmarking survey is primary source. | 2 days research |
|  | Benchmark comparison endpoint | GET /intelligence/benchmarks. Returns firm's actual metrics versus industry benchmarks for each dimension. Gap analysis with plain language description of what the gap means. | 1 day |
|  | Benchmark surface on dashboard | Section below morning briefing showing firm's position on each key metric versus industry average. Not a complex visualization. Simple comparison with gap highlighted. | 1 day |

## Ben — Persistent Assistant Agent — July

Once the concierge onboarding flow is complete Ben builds the persistent assistant. This is the always-available layer that answers how-to questions, finds features, surfaces relevant information based on what the firm is currently looking at, and logs every conversation as product intelligence.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Persistent assistant agent | Spins off from concierge when onboarding checklist is complete. Available on every page. Context-aware based on current entity being viewed. Answers how-to questions, explains features, suggests next steps. | Ben estimates |
|  | Agent conversation logging | Every question asked, every topic the agent handles, logged to behavioral_events table. event_type: agent.question_asked, entity_type: the feature or topic. This is continuous passive product research. | Half day |
|  | Agent usage correlation | Track whether firms using the agent more frequently have better outcome metrics. Surface this to the firm owner: firms that engage with the assistant complete engagements 20% faster on average. | Ben estimates |

# 06 — Month Three: Polish, QBO, Migration, and Launch Prep

August 1 through August 14. Two weeks. No new features after August 7th. Everything after that is testing, fixing, and preparing for launch.

## QBO Intelligence Layer — Andrew — First Week August

These builds make the workflow layer more complete and feed additional data into the intelligence layer. All high value. All relatively fast.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | QBO deep link | One click opens client QBO file from JAMM PX profile using realm ID. Already in session summary as a one hour build. Do this first. | 1 hour |
|  | AR aging detail | Replace basic QBO balance with full aging breakdown: current, 30, 60, 90 plus days. Uses ARAgingDetail report endpoint. | 1 day |
|  | Bookkeeping health score | Five signal composite from QBO data. ChangeDataCapture, BalanceSheet snapshots, ProfitAndLoss comparison, TransactionListByCustomer activity, GeneralLedger recency. Color coded status on client profile. | 3 days |
|  | ProfitAndLoss and BalanceSheet trend | Three months of each on client profile. Directional indicators: revenue up or down, expenses up or down, cash improving or deteriorating. | 2 days |
|  | QBO manual client link field | Link to QuickBooks customer field on client profile for manually added clients not synced via OAuth. | 2 hours |

## Migration and Onboarding Builds — Andrew — First Week August

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | TaxDome migration import | TaxDome-specific import endpoint mapping their export fields to JAMM PX client fields. Import wizard with source selector, preview of first 5 rows, confirm and import with results. | 3 days |
|  | Client list CSV import improvement | Current import accepts 5 fields. Expand to handle full client profiles. Deduplication with fuzzy name matching. | 1 day |
|  | IRS acknowledgment file parser | Firm drags and drops .ack file. System reads it and marks engagement as e-filed with confirmation number and timestamp. | 2 days |
|  | Full firm data export | GET /export/firm returning ZIP with clients.csv, engagements.csv, time_entries.csv, invoices.csv, irs_authorizations.csv, notes.csv, document_manifest.csv. Settings button firm owner only. | 1 day backend, 2 hours frontend |

## Lori's Feature List — Andrew — First Week August

Features surfaced in the firm owner conversation that are genuinely valuable and relatively fast to build.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Timesheet start/stop timer | Start and stop timer on time entry. Client name visible directly on time entry row. Timer auto-calculates hours on stop. | 1 day |
|  | Portal archive section | Prior year documents and past returns in collapsible section in client portal. Clients can access historical documents without cluttering the active todo view. | 1 day |
|  | Terminology customization | Firm renames Engagement, Client, Task to whatever they use firm-wide. Stored in firm settings. Applied throughout the UI via a terminology context. | 2 days |
|  | Sendable timesheet detail | Hours breakdown per engagement that staff can send to clients. Shows work performed, hours, rate, total. Client receives it for transparency before invoice. | 1 day |
|  | Custom sending domain wizard | DNS verification wizard for custom from-name and domain on all Postmark sends. Makes automated emails appear to come from the firm's own domain. | 1 day frontend, half day backend |
|  | Client portal PWA configuration | Progressive Web App config so clients can add portal to home screen. next.config.ts plus manifest.json plus service worker. Four hour configuration. | 4 hours |

## Frontend Polish and Completion — Andrew — Week Two August

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Automation rule simulator UI | Test this rule button on each automation row opens modal where firm fills in mock event payload and sees what would trigger. Backend POST /automation-rules/{id}/simulate is fully built. Zero frontend exists. | 1 day |
|  | IRS Publication 4557 compliance page | Compliance tab in Settings showing each requirement and its status. Download my security plan button generates PDF with firm name and JAMM security measures. No competitor does this. | 2 days |
|  | NPS settings frontend | Settings page where firms configure their Google review URL and enable the NPS flow. Backend is complete. | Half day |
|  | Skeleton screen audit | Every list page and data table must use skeleton screens not spinners. Audit all pages and add missing skeleton states. | 1 day |
|  | Complete application walkthrough | Walk the entire application as a firm owner. Document every UI inconsistency, missing empty state, broken flow, and confusing label. Fix everything found. | 2 days |

## Security and Pre-Launch Verification — Both — Week Two August

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Full pytest run | Run complete test suite. Document current passing count. Fix any failures that touch critical paths: auth, payments, document access, firm isolation. | 1 day |
|  | Stripe Connect end-to-end test | Test full sequence in test mode: connect Stripe, create invoice, client pays, invoice marks paid, webhook fires. Broken payment on day one kills trust. | 1 day |
|  | Tenant isolation verification | Confirm Firm A cannot access Firm B data across every endpoint. Run the tenant isolation test suite. | Half day |
|  | Production environment audit | Confirm all environment variables are production values. CORS locked. Rate limiting active. Security headers firing. No debug flags. | Half day |

## Ben — Email Infrastructure — All of Month Three

Ben's primary non-agent responsibility this summer. The email infrastructure must be ready before launch so outreach can begin immediately after.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Warm 20 inboxes | Continue warming all twenty inboxes through July and August. Maintain low volume. No sequences to the main lead list yet. | Ongoing |
|  | Small scale copy testing | Run low volume sequences to a small subset of verified leads to test copy variants. Never burn the main list. Goal is to have winning copy confirmed before launch. | Ongoing |
|  | Apollo list expansion and ZeroBounce verification | Expand lead list targeting two to thirty five staff tax and advisory firms. Verify all emails. Segment by firm size for sequence personalization. | Ongoing |
|  | LinkedIn scraping | Scrape firm owner profiles in target segments. Build the LinkedIn outreach list for post-launch direct outreach. | Ongoing |

# 07 — Loom Videos

Loom videos are not product walkthroughs. They are revelation moments. Each one shows the intelligence layer doing something a firm owner has never seen software do before. Written for Loom but also usable as the foundation for landing page copy.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Morning briefing revelation | Narrate a morning briefing that surfaces three real issues: a client about to miss a document deadline, an engagement being consumed by scope creep, and a staff member approaching unsustainable workload. Show how each one gets resolved from the briefing. | Half day |
|  | Pricing audit revelation | Show the fee schedule setup. Then show the pricing gap surface revealing that a firm is undercharging fourteen clients by an average of eight hundred dollars per year. Total number shown clearly. This is the one that makes firm owners stop scrolling. | Half day |
|  | Client health revelation | Show the client list with health indicators. Click into an amber client. Show the specific reasons: response time increasing over 60 days, portal logins declining, last engagement took longer than cohort average. Explain what this means before the client has said anything. | Half day |
|  | Full workflow demonstration | Show a complete engagement from creation to invoice paid without leaving the application. New client, new engagement, document request sent, client uploads via portal, return completed, invoice generated, client pays. Everything in one system. | 1 day |
|  | IRS authorization demonstration | Show authorization tracking, expiry alert, and the workflow that prevents a firm from attempting a transcript pull on an expired authorization. This is the feature no competitor has and most firm owners do not know they need until they have experienced the failure mode. | Half day |

# 08 — Go To Market — Summer Activities

## Andrew — Firm Owner Conversations

Three to five dedicated insight calls with firm owners before launch. Not sales calls. Research calls. The goal is to hear how firm owners describe the intelligence gap in their own language so that language appears on the landing page and in outreach copy.

The one question that must appear in every call: what would it be worth to you if you knew which of your clients were about to leave before they told you. Listen to how they answer. That answer is the pricing anchor and the headline.

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Schedule three to five insight calls | Target firm owners in the two to fifteen staff range. Warm connections first. Former colleagues, referrals from Lori, anyone in the Facebook CPA groups who has engaged with posts. | Ongoing June |
|  | Facebook CPA group presence | Post genuinely useful content in the groups. Not promotional. Questions, observations, research findings. Build recognition before outreach begins. | Weekly |
|  | Landing page rewrite | After insight calls provide language, rewrite the landing page around the intelligence positioning. Headline should reflect what firm owners said in their own words about the gap. Not feature list. Problem and revelation. | July |
|  | Pricing page design | Single tier. Three ninety nine per seat. Everything included. Two year guarantee. No upsells. No tiers. One decision. | July |

## Ben — Email and Outreach Infrastructure

| WHO | ITEM | DESCRIPTION | EST. TIME |
| --- | --- | --- | --- |
|  | Inbox warming — twenty inboxes | Maintain warming through the summer. Inboxes must be warm and healthy before any volume sequences run. | Ongoing |
|  | Copy testing at small scale | Test subject lines and email body variants on small verified subsets. Goal: confirmed winning variant for each sequence type before launch blitz. | July |
|  | Lead list build and verification | Apollo sourcing for two to thirty five staff tax and advisory firms. ZeroBounce verification on all. Segment by size for personalization. | June and July |
|  | Reddit presence — r/taxpros | Continue community engagement. Genuine contribution not promotion. Build name recognition in the community before the product is public. | Weekly |

# 09 — Build Sequence and Dependencies

This section maps the critical path. Some items must be done before others can start. Ben and Andrew should never be waiting on each other if the sequence is followed correctly.

## Andrew's Critical Path

- Critical fixes and mock data removal — nothing starts until this is done

- Behavioral event log expansion — must be complete before intelligence endpoints are built

- Fee schedule model and endpoint — morning briefing pricing gap depends on this

- Morning briefing backend — frontend cannot be built without it

- Morning briefing frontend — this is the demo centerpiece, must be compelling

- Intelligence layer features — profitability, churn prediction, growth readiness, benchmarks

- QBO intelligence layer — builds on existing QBO integration

- Migration and onboarding builds — TaxDome import, CSV improvement, .ack parser

- Lori's feature list — valuable but not blocking anything else

- Frontend polish and completion — last week before cutoff

- Full application walkthrough and fix — August 7th deadline for new features

- Security verification and pytest — August 8th through 14th

## Ben's Critical Path

- Complete concierge agent phases 2 through 6 — all of June

- Wire agent conversations to behavioral event log — must be done before any firm uses it

- Build persistent assistant agent — July, after concierge is complete

- Email infrastructure — warming and copy testing running in parallel throughout

- Security and production verification — August alongside Andrew

## Where Ben Might Wait on Andrew

The persistent assistant needs the morning briefing endpoint to exist so it can reference briefing items contextually. Andrew should have the morning briefing backend done by mid-July at the latest. If Andrew runs behind on this, Ben can build the assistant without the briefing integration and add it later.

The agent usage correlation feature needs the behavioral event log expansion to be complete so agent conversation events can be compared against outcome metrics. Andrew's event log expansion is week one and two of June. This is not a blocker for Ben but the correlation analysis cannot be built until it is done.

## Where Andrew Might Wait on Ben

Andrew should not be waiting on Ben for anything on the critical path. Ben's work is parallel. The only dependency is the concierge agent completion before Andrew can test the full onboarding flow end to end. Target: concierge complete by July 1st.

# 10 — Launch Readiness Checklist

Every item on this list must be confirmed complete before August 15th. If any item is not complete, launch moves to the following Monday. No exceptions.

## Product

- All mock data files removed. Every page hitting live API.

- Behavioral event log firing comprehensively. Verified in production.

- Morning briefing live and populated with real data.

- Pricing gap surface live on dashboard.

- Client profitability intelligence live.

- Industry benchmarks hard-coded and displaying.

- Fee schedule setup flow working end to end.

- Concierge onboarding agent complete and tested.

- Persistent assistant live on every page.

- TaxDome migration import working.

- Full firm data export working.

- Stripe Connect end-to-end verified in test mode.

- Dropbox Sign production key active.

- All known UI gaps fixed from application walkthrough.

- PWA configuration complete on client portal.

## Security

- CORS locked to production origins.

- Rate limiting active on auth endpoints.

- Staff JWT refresh tokens working.

- Tenant isolation verified across all endpoints.

- Security headers active in production.

- Stripe ca_placeholder replaced with real Connect client ID.

- AWS SES or Postmark domain verification confirmed.

## Go To Market

- Landing page rewritten around intelligence positioning.

- Pricing page live: three ninety nine per seat, everything included, two year guarantee.

- At least three Loom videos complete: morning briefing, pricing audit, full workflow.

- At least three firm owner insight calls completed.

- Outreach copy tested at small scale. Winning variant confirmed.

- Twenty inboxes warm and ready.

- Lead list built, verified, and segmented.

# The One Number That Matters

Everything in this document is in service of one outcome. Ten or more firms genuinely engaged on the platform by November 1st, 2026. That is the number that determines whether JAMM PX is on the realistic growth path or the conservative one.

Ten firms generating behavioral data means the benchmark starts to have meaning. Ten firms using the morning briefing means you have ten real feedback loops telling you what the intelligence layer is and is not catching. Ten firms going through their first tax season on JAMM PX means ten stories to tell in January 2027 when the next wave of firm owners starts evaluating their tools.

Build the product that makes those ten stories undeniable. Everything else follows.

JAMM PX — Summer Build Plan — May 2026 — Confidential