## Build Schedule
JAMM PX — Master Build Schedule ¦ Now → August 15, 2026 ¦ Chronological — both owners interleaved
Owner | Build Item | Est Days | Status | Notes / Dependencies
PRE-WEEK 1 — Now through Sunday Jun 1
Andrew clears the decks and builds all queued features. Ben finishes Concierge. Both start Monday clean.
PRE-LAUNCH FIXES — Andrew
Andrew | Remove all mock data from frontend — wire invoices, tasks, engagements to live API | 1 | ✅ Complete | Blocker. One Claude Code run. Nothing else ships until live API is wired.
Andrew | Staff JWT refresh tokens — staff cannot be logged out mid-session | 1 | ✅ Complete | Real work, not a quick fix
Andrew | CORS production config — lock backend to app.jammpx.com only | 0.25 | ✅ Complete | Config change ~20 mins. Currently accepts requests from any site.
Andrew | Remove index_consent gate from log_event — every firm contributes data by default | 0.25 | ✅ Complete | One Claude Code run
IN-QUEUE FEATURES + FEE SCHEDULE — Andrew
Andrew | Fee schedule model + complexity modifier UI — base fee per engagement type, modifier per flag, tiered adders for crypto and K-1s | 2 | ✅ Complete | Pricing gap endpoint depends on this. Build backend + settings UI together.
Andrew | Terminology customization per firm — Engagement/Client/Task renamed firm-wide via settings | 2 | 🟡 Waiting | Stored in firm settings. Terminology context applied throughout entire UI.
Andrew | Timesheet start/stop timer + client name visible directly on time entry rows | 1 | ✅ Complete | Timer auto-calculates hours on stop
Andrew | Portal archive — prior year documents and past returns in collapsible section in client portal | 1 | ✅ Complete | Keeps active todo view clean for clients
Andrew | QBO manual client link field — Link to QuickBooks customer on client profile for manually added clients | 0.5 | ✅ Complete | For clients not synced via OAuth
Andrew | Sendable timesheet detail — hours breakdown per engagement, client-receivable for transparency before invoice | 1 | ✅ Complete
CONCIERGE AGENT — Ben (complete by Sunday)
Ben | Concierge agent remaining phases — complete and tested | 4 | 🔵 In Progress | Ben estimated 4 days from yesterday. Target: Sunday.
WEEK 1 — Jun 2–8
Andrew: email OAuth first — unlocks Ben's email layer items early. Then QBO begins. Ben: application builds + benchmark research opens.
EMAIL OAUTH + QBO BEGINS — Andrew
Andrew | Gmail OAuth integration — connect firm Gmail, read thread metadata only, no content stored ever | 2 | ✅ Complete | Do this first. Unlocks Ben's four email layer items. Behavioral signals only — response lag, thread depth, contact frequency.
Andrew | Outlook OAuth integration — same behavioral signal extraction as Gmail | 2 | ✅ Complete
Andrew | QBO deep link — one click opens client QBO file from JAMM PX profile using realm ID | 0.5 | ✅ Complete | Realm ID already stored from OAuth. ~1 hour.
Andrew | AR aging detail — replace basic QBO balance with current/30/60/90+ day breakdown | 1 | ✅ Complete | ARAgingDetail report endpoint
CONCIERGE WIRED + APPLICATION BUILDS + BENCHMARK RESEARCH BEGINS — Ben
Ben | Wire Concierge conversation events to behavioral event log | 0.5 | ⬜ Not Started | Do immediately after Concierge ships. Every question asked = product intelligence signal.
Ben | TaxDome migration import — field mapping, import wizard, preview + confirm | 3 | ✅ Complete | Establish the migration pattern first. Note: Financial Cents and Karbon require export format research before scoping — may not have clean export paths.
Ben | Full firm data export — ZIP with all CSVs (clients, engagements, invoices, IRS auths, notes, docs manifest) | 1 | ✅ Complete | Settings button, firm owner only
Ben | CSV + QuickBooks import wizard frontend (12B-10) — step-by-step wizard UI | 1 | ✅ Complete | Backend already complete. Frontend only.
Ben | Benchmark research — Metric 1: Engagement Velocity (AICPA PCPS, state CPA societies, practice mgmt surveys) | 1 | ⬜ Not Started | Research runs alongside builds. Spread across Weeks 1-3. Compile into handoff doc for Andrew by end of Week 3.
Ben | Benchmark research — Metric 2: Document Collection Speed | 1 | ⬜ Not Started
WEEK 2 — Jun 9–15
Internship starts Jun 8. Andrew on reduced hours — QBO intelligence layer completes. Ben: migrations, quick polish items, benchmark research continues.
QBO INTELLIGENCE LAYER COMPLETE — Andrew
Andrew | Bookkeeping health score — 5-signal composite (ChangeDataCapture, BalanceSheet, P&L, TransactionList, GL recency) | 3 | ✅ Complete | Color coded status on client profile and list
Andrew | P&L and BalanceSheet trend — 3 months, directional indicators on client profile | 2 | ✅ Complete | Revenue up/down, expenses, cash position improving or deteriorating
Andrew | Budget variance alert automation — compare QBO budget to actual P&L, fire task on deviation | 3 | ✅ Complete
Andrew | CustomerIncome report on client profile — revenue this client has generated over selectable period | 1 | ✅ Complete
Andrew | CashFlow report on client profile — monthly cash flow trend without opening QBO | 1 | ✅ Complete
MIGRATIONS + QUICK POLISH + BENCHMARK RESEARCH — Ben
Ben | Research Financial Cents and Karbon export formats — confirm whether clean import is possible before scoping | 1 | ✅ Complete | If export format exists: build import. If not: flag as post-launch. Do not assume it's buildable.
Ben | Financial Cents migration import — follows TaxDome pattern (pending research above) | 2 | ✅ Complete | Depends on: export format research confirms viable path
Ben | Karbon migration import — follows TaxDome pattern (pending research above) | 2 | ✅ Complete | Depends on: export format research confirms viable path
Ben | IRS Publication 4557 compliance page + downloadable security plan PDF | 0.25 | ⬜ Not Started | Upload IRS requirements + codebase snapshot to Claude. Generates compliance mapping. ~20 mins.
Ben | Password policy configuration | 1 | ✅ Complete
Ben | Session timeout configuration | 1 | ✅ Complete
Ben | Failed login alert | 0.5 | ✅ Complete
Ben | PWA configuration on client portal — manifest.json + service worker, add to home screen | 0.5 | ✅ Complete
Ben | Skeleton screen audit — every list page and data table uses skeletons not spinners | 1 | ✅ Complete
Ben | Automation rule simulator UI — Test this rule modal, frontend for existing POST endpoint | 1 | ✅ Complete | Backend POST /automation-rules/{id}/simulate already fully built
Ben | NPS settings frontend — Google review URL config, enable NPS flow | 0.5 | ✅ Complete | Backend complete
Ben | Benchmark research — Metric 3: Invoice Payment Time | 1 | ⬜ Not Started
Ben | Benchmark research — Metric 4: Portal Adoption Rate | 1 | ⬜ Not Started
WEEK 3 — Jun 16–22
Andrew: tax software workarounds. Ben: persistent assistant agent + benchmark research complete.
TAX SOFTWARE WORKAROUNDS — Andrew
Andrew | Client list CSV import expansion — handle full client profiles, fuzzy dedup (beyond current 5 fields) | 1 | ✅ Complete
Andrew | IRS acknowledgment file parser — drag/drop .ack file, auto-mark engagement e-filed with confirmation number | 2 | ✅ Complete
Andrew | File watcher agent — local install on firm machine, monitors tax software output folder, auto-updates JAMM PX | 5 | 🟡 Waiting | One executable, no config required for firm. Most uncertain estimate on the board. Does not block anything downstream.
PERSISTENT ASSISTANT + BENCHMARK RESEARCH COMPLETE — Ben
Ben | Persistent assistant agent — context-aware, every page, answers how-to, suggests next steps | 5 | ⬜ Not Started | Depends on: Concierge complete. Spins off from Concierge architecture.
Ben | Benchmark research — Metric 5: Automation Utilization | 1 | ⬜ Not Started
Ben | Benchmark research — Metric 6: Deadline Adherence | 1 | ⬜ Not Started | All 6 metrics complete end of Week 3. Compile into single handoff doc with sources. Andrew needs this in Week 8.
Ben | Demo seed data research begins — what does a realistic firm look like, full tax season activity, what makes morning briefing say something real | 2 | ⬜ Not Started | Research phase only. Implementation happens in Week 7 once morning briefing endpoint exists. Dispersed across Weeks 3-6.
WEEK 4 — Jun 23–29
Intentionally lighter — overflow buffer from Weeks 1-3. Andrew: synthesis layer begins early. Ben: email layer items + portal agent + demo research continues.
SYNTHESIS LAYER BEGINS EARLY — Andrew
Andrew | Statistical aggregation pipeline — event log → metric calculations → time-series storage | 2 | ⬜ Not Started | Foundation everything else connects to. Build this first. Flag Ben when pipeline is producing output — he starts correlation scanning layer immediately on that signal regardless of week.
Andrew | Confidence gate — statistical significance scoring, nothing surfaces below threshold | 1 | ⬜ Not Started | Gate is high early. Self-calibrates as RL matures. Build alongside aggregation pipeline.
Andrew | Anomaly detection — deviation from firm's own historical baseline, no hardcoded definition of normal (scikit-learn) | 2 | ⬜ Not Started | Begins here if Week 4 has runway, otherwise opens Week 5
EMAIL LAYER ITEMS + PORTAL AGENT + DEMO RESEARCH — Ben
Ben | Email behavioral event firing — sent to known client, response lag, thread depth logged (no content ever) | 1 | ✅ Complete | Depends on: Andrew's Gmail + Outlook OAuth complete (Week 1)
Ben | Local NLP sentiment classifier — positive/neutral/frustrated/urgent (HuggingFace, runs entirely locally) | 2 | ⬜ Not Started | No content leaves infrastructure. Opt-in at firm level.
Ben | Custom sending domain wizard — DNS verification, white-label Postmark sends from firm's own domain | 1.5 | ✅ Complete
Ben | Custom portal domain per firm — DNS wizard, white-label portal URL | 1.5 | ✅ Complete
Ben | Wire persistent assistant + email agent events to behavioral log | 0.5 | ⬜ Not Started | Same pattern as Concierge wiring. Do immediately after assistant ships.
Ben | Client portal agent — narrowly scoped to document guidance, invoice questions, engagement status, portal how-to only | 3 | ⬜ Not Started | Scoped to portal JWT only. Shows disclaimer upfront. Never gives tax advice. Never exposes firm-internal data. Separate build from persistent assistant.
Ben | Demo seed data research continues — realistic engagement mix, client roster, seasonal patterns | 1 | ⬜ Not Started | Research phase. Ongoing Weeks 3-6.
WEEK 5 — Jun 30–Jul 6
Intentionally light. Tracking pass + overflow buffer. Andrew: synthesis layer continues. Ben: landing page agent + demo research.
COMPREHENSIVE EVENT LOG EXPANSION — Andrew (one big pass)
Andrew | Engagement events — deadline_changed, reopened, archived, revision cycles, scope creep, complexity flags | 1 | ⬜ Not Started | All features exist now. One comprehensive Claude Code session covers everything.
Andrew | Document events — viewed, downloaded, deleted, failed uploads, upload sequence pattern per client | 0.5 | ⬜ Not Started
Andrew | Invoice events — viewed, adjusted downward, late fee assessed/waived, payment plan created, write-off | 0.5 | ⬜ Not Started
Andrew | Portal events — session depth, page sequence within session, device type, time-of-day patterns | 0.5 | ⬜ Not Started
Andrew | Staff events — time entry lag, complexity tier per assignment, feature opened and abandoned, session abandonment | 0.5 | ⬜ Not Started
Andrew | Firm events — feature adoption sequence, automation override, template modification delta, settings change frequency | 0.5 | ⬜ Not Started
Andrew | Fee schedule behavioral events — calculator runs, manual overrides, acceptance outcomes per engagement | 0.5 | ⬜ Not Started
Andrew | Client creation events — referral source structured field, referring client ID if applicable | 0.5 | ⬜ Not Started
Andrew | Staff profile events — skill set tags, loaded hourly cost, firm location zip code | 0.5 | ⬜ Not Started
Andrew | Agent interaction events — Concierge + assistant + portal agent: topic categories, steps, abandonment, query-to-action | 0.5 | ⬜ Not Started | Depends on all three agents complete
Andrew | Intelligence output events — placeholder wired now, fully populated after synthesis layer built | 0.5 | ⬜ Not Started
Andrew | Anomaly detection continues if not complete from Week 4 | 1 | ⬜ Not Started
Andrew | Sequence pattern mining — finds A→B→C causal chains across firms (statsmodels) | 2 | ⬜ Not Started | Requires repeated instances across firms to confirm — not single occurrences
LANDING PAGE AGENT + PORTAL AGENT WIRED + DEMO RESEARCH — Ben
Ben | Wire portal agent events to behavioral log — questions asked, topics, session depth | 0.5 | ⬜ Not Started
Ben | Landing page AI agent — handles objections, features, pricing, captures lead for real call | 5 | ⬜ Not Started | Similar architecture to Concierge but public-facing
Ben | Demo seed data research continues — financial patterns, document volumes, engagement velocity numbers | 1 | ⬜ Not Started | Research phase. Ongoing Weeks 3-6.
WEEK 6 — Jul 7–13
Stripe lands (hopefully). Andrew: synthesis layer deep build. Ben: ML pieces begin + correlation layer on Andrew's signal.
SYNTHESIS LAYER DEEP BUILD — Andrew
Andrew | Stripe Connect full activation — replace placeholder with live Connect client ID | 1 | 🟡 Waiting on Mercury | Do immediately when Mercury account + LLC articles land. Do not wait for a scheduled week.
Andrew | Firm memory model — longitudinal baseline per firm, feeds anomaly detection, irreplaceable after 6 months | 1 | ⬜ Not Started | Clock starts day one. This is what makes JAMM PX impossible to leave.
Andrew | Correlation engine — Andrew's piece: scans all metric combinations for statistically significant relationships | 2 | ⬜ Not Started | When aggregation pipeline output is confirmed running, flag Ben immediately. Ben starts his scanning layer on that signal.
Andrew | Morning briefing backend endpoint — reads all domains, urgency scoring, returns structured plain language items | 2 | ⬜ Not Started | Depends on: event log expansion complete, fee schedule built
Andrew | Urgency scoring algorithm — weights deadline proximity, financial risk, client health, staff workload, historical patterns | 1 | ⬜ Not Started | Items sorted by composite urgency score not by category
ML LAYER BEGINS + DEMO RESEARCH FINALIZES — Ben
Ben | Clustering algorithms — groups firms into natural behavioral cohorts (scikit-learn KMeans/DBSCAN) | 2 | ⬜ Not Started | Makes benchmarks accurate. Firms compared to behavioral peers not just firm size.
Ben | Time series forecasting — projects metric trajectories forward so warnings arrive before outcome (Prophet, local) | 2 | ⬜ Not Started | Well-documented library. Clear interface against Andrew's aggregation pipeline.
Ben | Correlation engine — Ben's piece: systematic metric combination scanning layer | 2 | ⬜ Not Started | 🔴 Cannot start until Andrew flags that aggregation pipeline is producing output. Andrew's pipeline output is the defined input interface.
Ben | Demo seed data research finalizes — all data points gathered, ready for implementation in Week 7 | 1 | ⬜ Not Started | Research phase complete. Implementation next week.
Ben | Agent usage correlation — firms using assistant more correlate with better outcome metrics | 1 | ⬜ Not Started | Depends on: event log expansion complete
WEEK 7 — Jul 14–20
Andrew: visible intelligence surfaces. Ben: ML layer complete + demo seed data implemented.
VISIBLE INTELLIGENCE SURFACES — Andrew
Andrew | Pricing gap calculation endpoint — actual billed vs fee schedule + complexity flags, per client and firm-wide | 1 | ⬜ Not Started | Depends on fee schedule model
Andrew | Client profitability calculation endpoint — revenue minus staff cost, sorted by margin | 1 | ⬜ Not Started | Depends on staff hourly cost field
Andrew | Churn prediction signals — response time increasing, portal logins declining, engagement count declining YoY | 1 | ⬜ Not Started | Surface in client health indicator and morning briefing
Andrew | Client satisfaction pulse — single question post-engagement, 1-5 scale, auto-sent via Postmark | 0.5 | ⬜ Not Started | NPS backend already built — wire to this flow
Andrew | Capacity projection endpoint — pipeline vs historical completion rates vs staff available hours | 1 | ⬜ Not Started
Andrew | Growth readiness surface — revenue per staff vs industry benchmark, specific hire threshold calculation | 1 | ⬜ Not Started | Evidence-based hire decision not gut feel
Andrew | Pricing drift detection — flag fee schedules unchanged 12+ months, complexity grew but fees did not | 0.5 | ⬜ Not Started
Andrew | Industry benchmark hard-coded data — AICPA PCPS values for all 6 metrics, labeled industry-sourced | 1 | ⬜ Not Started | Depends on: Ben benchmark research handoff doc complete (end of Week 3)
Andrew | Benchmark comparison endpoint — firm actual vs industry benchmark, gap analysis, plain language | 1 | ⬜ Not Started
ML LAYER COMPLETE + DEMO SEED DATA IMPLEMENTED — Ben
Ben | Graph analysis — maps staff/client/engagement relationship networks, referral chains, automation sequences | 1 | ⬜ Not Started | Finds structural patterns in relationships not just metric values
Ben | Reinforcement learning foundation — learns which interventions work, runs silently from day one | 2 | ⬜ Not Started | Low confidence outputs NEVER surface early. Must be live day one — cannot recover retroactively.
Ben | Demo seed data implementation — seed realistic firm data into demo environment, verify morning briefing populated | 2 | ⬜ Not Started | Implementation phase. Research complete from prior weeks. Must be done before Loom videos.
WEEK 8 — Jul 21–27
Andrew: intelligence layer completes. Ben: intelligence frontend begins as Andrew hands off endpoints.
INTELLIGENCE LAYER COMPLETE — Andrew
Andrew | Seven-category cockpit backend — highest severity confirmed finding per category surfaced | 2 | ⬜ Not Started | Seven categories: client relationships, engagement ops, revenue, staff, business health, growth, intelligence alerts
Andrew | Deficiency surfacing layer — where firm stands vs cohort on each metric. Layer one. Visible at launch. | 1 | ⬜ Not Started | Non-obvious because no firm knows how they compare without it. Requires no ML learning time.
Andrew | Anthropic API narrative layer — strips firm identity, sends confirmed finding, receives plain language, reattaches | 1 | ⬜ Not Started | AI never finds connections. ML does. AI only translates confirmed findings into plain language.
Andrew | Three-option dismissal feedback loop — not relevant / already handling / incorrect | 1 | ⬜ Not Started | Each option is a different RL calibration signal. Binary dismissal provides almost no useful information.
Andrew | Wire intelligence output events to behavioral log — briefing viewed, item acted/dismissed, prediction accuracy | 0.5 | ⬜ Not Started | Final event log wiring pass. Completes the full tracking schema.
INTELLIGENCE FRONTEND BEGINS — Ben (as Andrew hands off each endpoint)
Ben | Morning briefing frontend — replaces dashboard hero, plain language items, acted/dismissed tracking per item | 2 | ⬜ Not Started | Depends on: Andrew's morning briefing endpoint (Week 6)
Ben | Seven-category cockpit UI — one finding per category, severity indicators, blank states for unconfident data | 3 | ⬜ Not Started | Depends on: Andrew's seven-category cockpit backend
Ben | Benchmark comparison surface — firm position on each metric vs industry average, gap highlighted | 1 | ⬜ Not Started | Depends on: Andrew's benchmark endpoint
Ben | Client profitability UI — indicator on client list + detail, color coded, firm owner and manager only | 1 | ⬜ Not Started | Depends on: Andrew's profitability endpoint
Ben | Landing page — intelligence positioning, savings calculator, Loom embed placeholders | 2 | ⬜ Not Started | Depends on: insight call language from Andrew. Hard deadline this week — must be done before Loom videos.
WEEK 9 — Jul 28–Aug 3
Intelligence frontend completes. QA window opens. Both heads down simultaneously — no handoffs needed mid-week.
QA — Andrew
Andrew | Pytest coverage — all Andrew-built modules, critical paths, tenant isolation, auth | 3 | ⬜ Not Started
Andrew | Tenant isolation verification — confirm Firm A cannot access Firm B data across every endpoint | 1 | ⬜ Not Started
INTELLIGENCE FRONTEND COMPLETE + QA — Ben
Ben | Individual findings pages — full findings per category ranked by severity, behind cockpit | 2 | ⬜ Not Started
Ben | JAMM Index UI — founding firm contribution, trajectory graphs, benchmark positioning over time | 2 | ⬜ Not Started | Sections show building your profile state when data is thin. Never show blank with no explanation.
Ben | Intelligence alert surfaces — churn prediction, pricing drift, capacity warnings surfaced in context | 1 | ⬜ Not Started
Ben | Growth readiness and capacity projection surfaces | 1 | ⬜ Not Started | Depends on: Andrew's capacity and growth endpoints
Ben | Pytest coverage — all Ben-built modules | 3 | ⬜ Not Started
WEEK 10 — Aug 4–10
🔴 FINAL WEEK. No new features after Aug 7. QA, Loom videos, production audit, launch prep.
FINAL QA + PRODUCTION AUDIT — Both
Both | Full application walkthrough — every flow tested end to end on production, every issue documented and fixed | 2 | ⬜ Not Started | Ben owns the fixes found here
Both | Stripe Connect end-to-end test — connect, create invoice, client pays, webhook fires, invoice marks paid | 1 | ⬜ Not Started | Broken payment on day one kills trust
Both | Production environment audit — all env vars confirmed production, CORS locked, rate limiting active, no debug flags | 0.5 | ⬜ Not Started
LOOM VIDEOS — Both
Both | Loom: Morning briefing revelation — three real issues surfaced and resolved | 0.5 | ⬜ Not Started | Requires demo seed data and morning briefing live with real numbers
Both | Loom: Pricing audit revelation — fee schedule + undercharging dollar gap | 0.5 | ⬜ Not Started
Both | Loom: Client health revelation — amber client deep dive with specific behavioral signals | 0.5 | ⬜ Not Started
Both | Loom: Full workflow demonstration — engagement creation to invoice paid without leaving JAMM PX | 1 | ⬜ Not Started
Both | Loom: IRS authorization demonstration — expiry alert, transcript pull prevention | 0.5 | ⬜ Not Started
LANDING PAGE FINALIZED + ONGOING — Ben + Both
Ben | Landing page — Loom videos embedded, savings calculator live, copy finalized | 1 | ⬜ Not Started
Both | Firm owner insight calls — 3-5 minimum, research not sales, language goes to landing page copy | 0 | ⬜ Not Started | Ongoing Jun–Jul. Andrew sources: Lori referrals, Facebook CPA groups, warm contacts.
🚀 AUGUST 15, 2026 — LAUNCH
Every event firing. Every surface live. Every ML piece installed and learning silently from day one.
Both | 🚀 LAUNCH — JAMM PX live | 0 | ⬜ Not Started

## Dependency Map
JAMM PX — Critical Dependency Map ¦ Upstream must be complete before Downstream can start
Upstream — must exist first |  | Downstream — cannot start until | Notes
Pre-launch fixes complete (Andrew) | → | Everything else | Mock data + JWT + CORS are day 1 blockers
Concierge agent complete (Ben) | → | Persistent assistant agent (Ben) | Assistant spins off from Concierge architecture
Concierge complete (Ben) | → | Wire Concierge events to behavioral log (Ben) | Can't log what doesn't exist yet
Persistent assistant complete (Ben) | → | Client portal agent (Ben) | Same architecture pattern, scoped to portal JWT
Gmail + Outlook OAuth complete (Andrew, Week 1) | → | Ben's four email layer items (Week 4) | Email events, NLP, sending domain, portal domain all depend on OAuth
Fee schedule model built (Andrew, Pre-Week 1) | → | Pricing gap endpoint (Andrew, Week 7) | Can't calculate gap without target fees
Staff hourly cost field (Andrew, Pre-Week 1) | → | Client profitability endpoint (Andrew, Week 7) | Can't calculate margin without loaded cost
TaxDome import working (Ben, Week 1) | → | Financial Cents + Karbon imports (Ben, Week 2) | Pattern established with TaxDome first
Financial Cents + Karbon export format research (Ben) | → | Financial Cents + Karbon import builds | Do not build imports until export format is confirmed viable
All features built — both owners | → | Comprehensive tracking pass (Andrew, Week 5) | Track everything in one pass after all surfaces exist
Event log expansion complete (Andrew, Week 5) | → | Statistical aggregation pipeline (Andrew) | ML has nothing meaningful to learn from without comprehensive events
Event log expansion complete (Andrew, Week 5) | → | Agent usage correlation (Ben) | Correlation needs full event history
Andrew flags: aggregation pipeline producing output | → | Ben: correlation scanning layer begins | Milestone-dependent not week-dependent. Ben starts immediately on Andrew's signal.
Statistical aggregation pipeline (Andrew) | → | All ML builds — anomaly, sequence, clustering, RL, time series | Foundation everything else connects to
Ben benchmark research handoff doc — all 6 metrics | → | Industry benchmark hard-code (Andrew, Week 7) | Andrew needs compiled AICPA numbers with sources
Andrew: morning briefing endpoint (Week 6) | → | Ben: morning briefing frontend (Week 8) | Ben cannot build UI without the API
Andrew: seven-category cockpit backend (Week 8) | → | Ben: cockpit UI (Week 8)
Andrew: profitability endpoint (Week 7) | → | Ben: profitability UI (Week 8)
Andrew: capacity + growth endpoints (Week 7) | → | Ben: capacity + growth surfaces (Week 9)
Ben: demo seed data implemented (Week 7) | → | All 5 Loom videos (Week 10) | Morning briefing needs real data to say something meaningful
Insight call language from Andrew | → | Landing page copy finalized (Ben, hard deadline Week 8) | Copy should sound like firm owners wrote it
Mercury account + LLC articles | → | Stripe Connect activation (Andrew) | Hard external dependency. Do not wait for a scheduled week — activate immediately when it lands.
All builds complete, pytest passing | → | 🚀 Launch August 15 | No new features after August 7

## Launch Checklist
JAMM PX — Launch Readiness Checklist ¦ Every item ✅ before August 15, 2026
Owner | Item | Status | Notes
INFRASTRUCTURE + SECURITY
Andrew | All mock data removed — every page hitting live API | ⬜ Not Started
Andrew | Staff JWT refresh tokens working | ⬜ Not Started
Andrew | CORS locked to production origins only | ⬜ Not Started
Andrew | index_consent gate removed — all firms contribute data by default | ⬜ Not Started
Andrew | Stripe ca_placeholder replaced with live Connect client ID | ⬜ Not Started | Waiting on Mercury
Andrew | Dropbox Sign production key active | ⬜ Not Started | Already done — confirm in production config
Andrew | Postmark confirmed handling all outbound email | ⬜ Not Started | AWS SES removed
Andrew | Rate limiting active on auth endpoints | ⬜ Not Started | Already built
Andrew | Tenant isolation verified across all endpoints | ⬜ Not Started
Andrew | Security headers active in production | ⬜ Not Started
Ben | Password policy configuration live | ⬜ Not Started
Ben | Session timeout configuration live | ⬜ Not Started
Ben | Failed login alert live | ⬜ Not Started
WORKFLOW LAYER — COMPLETE FEATURE SET
Andrew | Fee schedule + complexity modifiers working end to end | ⬜ Not Started
Andrew | Terminology customization working firm-wide | ⬜ Not Started
Andrew | Timesheet timer + client name on entries | ⬜ Not Started
Andrew | Portal archive working | ⬜ Not Started
Andrew | Sendable timesheet detail working | ⬜ Not Started
Andrew | QBO intelligence layer — all 7 builds live | ⬜ Not Started | Deep link, aging, health score, P&L, budget variance, income, cash flow
Andrew | Tax software workarounds — CSV import expansion, .ack parser, file watcher | ⬜ Not Started
Andrew | Email integration — Gmail + Outlook OAuth, behavioral signals firing | ⬜ Not Started
Ben | NLP sentiment classifier running locally — no content leaves infrastructure | ⬜ Not Started
Ben | Custom sending domain wizard live | ⬜ Not Started
Ben | Custom portal domain per firm live | ⬜ Not Started
Ben | TaxDome migration import working | ⬜ Not Started
Ben | Financial Cents + Karbon imports working (if export format confirmed viable) | ⬜ Not Started | Research required first — do not assume buildable
Ben | Full firm data export working | ⬜ Not Started
Ben | CSV + QB import wizard frontend live | ⬜ Not Started
Ben | Skeleton screen audit complete | ⬜ Not Started
Ben | Automation rule simulator UI live | ⬜ Not Started
Ben | NPS settings frontend live | ⬜ Not Started
Ben | IRS 4557 compliance page + security plan PDF downloadable | ⬜ Not Started
Ben | PWA configuration on client portal | ⬜ Not Started
Ben | Concierge agent complete and tested | ⬜ Not Started
Ben | Persistent assistant live on every page | ⬜ Not Started
Ben | Client portal agent live — narrowly scoped, disclaimer shown, no firm-internal data exposed | ⬜ Not Started
Ben | Landing page AI agent live | ⬜ Not Started
INTELLIGENCE LAYER — FULL INSTALLATION
Andrew | Behavioral event log firing comprehensively across all domains — verified in production | ⬜ Not Started
Andrew | Statistical aggregation pipeline running | ⬜ Not Started
Andrew | Anomaly detection installed and running silently | ⬜ Not Started
Andrew | Sequence pattern mining installed | ⬜ Not Started
Andrew | Confidence gate active — gate high early, self-calibrates over time | ⬜ Not Started
Andrew | Firm memory model running per firm from day one | ⬜ Not Started
Andrew | Correlation engine running — Andrew's piece | ⬜ Not Started
Andrew | Morning briefing endpoint live | ⬜ Not Started
Andrew | Pricing gap surface live | ⬜ Not Started
Andrew | Client profitability intelligence live | ⬜ Not Started
Andrew | Churn prediction signals live | ⬜ Not Started
Andrew | Capacity projection live | ⬜ Not Started
Andrew | Growth readiness surface live | ⬜ Not Started
Andrew | Industry benchmarks hard-coded and displaying — labeled industry-sourced | ⬜ Not Started
Andrew | Benchmark comparison surface live | ⬜ Not Started
Andrew | Seven-category cockpit backend live | ⬜ Not Started
Andrew | Anthropic API narrative layer wired — firm identity never touches API | ⬜ Not Started
Andrew | Three-option dismissal feedback loop live | ⬜ Not Started
Andrew | Intelligence output events wired to behavioral log | ⬜ Not Started
Ben | Clustering algorithms installed | ⬜ Not Started
Ben | Time series forecasting installed — Prophet running locally | ⬜ Not Started
Ben | Graph analysis installed | ⬜ Not Started
Ben | Reinforcement learning foundation installed and running silently from day one | ⬜ Not Started
Ben | Correlation engine — Ben's scanning layer installed | ⬜ Not Started
Ben | Morning briefing frontend live | ⬜ Not Started
Ben | Seven-category cockpit UI live — blank states for unconfident data | ⬜ Not Started
Ben | JAMM Index UI live | ⬜ Not Started
Ben | Individual findings pages live | ⬜ Not Started
Ben | Intelligence alert surfaces live | ⬜ Not Started
Ben | Growth readiness and capacity projection surfaces live | ⬜ Not Started
GO TO MARKET
Ben | Landing page rewritten around intelligence positioning — copy from insight calls | ⬜ Not Started
Ben | Demo seed data environment ready — morning briefing populated with real numbers | ⬜ Not Started
Both | Loom: Morning briefing revelation | ⬜ Not Started
Both | Loom: Pricing audit revelation | ⬜ Not Started
Both | Loom: Client health revelation | ⬜ Not Started
Both | Loom: Full workflow demonstration | ⬜ Not Started
Both | Loom: IRS authorization demonstration | ⬜ Not Started
Both | 3+ firm owner insight calls completed | ⬜ Not Started | Research not sales
Both | Full application walkthrough audit complete — all issues resolved | ⬜ Not Started
Both | Stripe Connect end-to-end verified in test mode | ⬜ Not Started
Both | Production environment audit complete | ⬜ Not Started