## AI Instructions
JAMM PX — AI INSTRUCTIONS SHEET
PRODUCT NAME — ALWAYS USE THIS
Product name: JAMM PX (short form) or JAMM Practice Experience (full form). NEVER use 'JAMM OS' — this name is retired.
PURPOSE OF THIS FILE
This file is the single source of truth for building JAMM PX — a practice experience SaaS platform built specifically for small tax and advisory firms (2-10 staff). It is optimised for use by an AI coding assistant directed by a non-technical founder.
CURRENT BUILD STATE — April 21 2026
Backend: ALL phases complete (Phases 1–11E). 373 tests passing, 2 skipped, 8 failing (security header tests — expected in dev mode, pass in production).
Frontend (Phase 12): Substantially complete. See Phase 12 sheet for item-by-item status.
Alembic: 28 migrations applied. Head confirmed.
Dev login: admin@demofirm.com / password123 (Demo Firm)
PRODUCT IDENTITY
JAMM PX pioneers the Practice Experience category — not practice management. It replaces 4-5 disconnected tools with one unified system.
Target user: Firm owner or staff at a 2-10 person tax or advisory firm.
Core promise: Automate the entire client work cycle from engagement creation to invoice payment, enterprise-grade security at a flat per-firm price.
PRICING MODEL
Starter: $99/mo, month-to-month, up to 2 staff
Professional: $199/mo, month-to-month, unlimited staff
Tax Firm: $299/mo, annual only, full product + white glove
Founding member offer: First 25 firms get Professional at $199/mo locked for life.
DOMAIN LANGUAGE — NEVER SUBSTITUTE SYNONYMS
Firm = the accounting business that pays for and uses JAMM PX
Client = the accounting firm's customer
Engagement = a unit of billable work. NEVER call this a 'Project'
Task = a discrete action item belonging to both a Client and an Engagement
Document Request = a checklist sent to a client asking them to upload specific files
Automation Rule = an if/then trigger that fires actions automatically
Staff = employees of the firm who use JAMM PX internally
Practice Experience = the category JAMM PX pioneers. Never use 'practice management'.
TECH STACK — NEVER DEVIATE WITHOUT EXPLICIT INSTRUCTION
Backend: FastAPI, PostgreSQL 14+, SQLAlchemy ORM 2.0 (Mapped[] syntax only), Pydantic v2, Alembic, Uvicorn + Gunicorn, Docker
Frontend: Next.js 14+ App Router, TypeScript, Tailwind CSS, shadcn/ui, Axios with JWT interceptor, TanStack Query
Infrastructure: AWS S3 (signed URLs only, never public), AWS SES, Stripe Connect, Dropbox Sign for e-signatures
KEY ARCHITECTURE RULES
firm_id always server-side — never in Create schemas, always injected from JWT
SQLAlchemy 2.0 select() style only — older query style is off-limits
Background tasks must create their own SessionLocal() — never inherit request session
Enums with dots or special characters: use native_enum=False, store as VARCHAR
Routers are thin — no business logic ever
Signed URLs only for all file access — never public S3 URLs, 1 hour maximum expiry
Migration procedure: verify current → generate → READ the file → apply → confirm. Never skip reading.
DEV STARTUP SEQUENCE — ALWAYS USE THIS
Terminal 1 (Backend): cd project root → .venv\Scripts\Activate.ps1 → python -m uvicorn app.main:app
Terminal 2 (Frontend): cd frontend → npm run dev
NEVER use --reload flag — crashes uvicorn on Windows
If login fails: run python -m scripts.seed to recreate demo data
HOW TO READ THE ROADMAP SHEETS
Sheet 'Execution Roadmap': Phases 0-12. All backend phases complete. Frontend Phase 12 in progress.
Sheet 'Phase 12 Frontend': Detailed frontend task list with current status per item.
Sheet 'Expansion Roadmap': Phases 13+. Build after first paying customer.
STATUS KEY: ✅ Complete 🔵 Partial/Backend Complete ❌ Not Built ⚠️ Manual Task

## Execution Roadmap
Seq | Phase | Module | Feature | Backend Task | Frontend Task | Status
✅ PHASES 0–11E COMPLETE — All backend phases done. 373 tests passing.
1 | 1 - Multi-Tenancy | Rename | Project→Engagement rename | ✅ Complete | N/A | ✅ Complete
2 | 1 - Multi-Tenancy | Multi-Tenancy | Firm model | ✅ Complete | N/A | ✅ Complete
3 | 1 - Multi-Tenancy | Multi-Tenancy | firm_id on all models | ✅ Complete | N/A | ✅ Complete
4 | 1 - Multi-Tenancy | Multi-Tenancy | Tenant guard dependency | ✅ Complete | N/A | ✅ Complete
5 | 1 - Multi-Tenancy | Multi-Tenancy | Tenant isolation enforcement | ✅ Complete | N/A | ✅ Complete
6 | 1 - Multi-Tenancy | RBAC | Role model + permissions | ✅ Complete | N/A | ✅ Complete
7 | 1 - Multi-Tenancy | RBAC | Session invalidation on role change | ✅ Complete | N/A | ✅ Complete
8 | 2 - CRM Core | Engagements | Engagement model + tax deadlines | ✅ Complete | ✅ Complete | ✅ Complete
9 | 2 - CRM Core | Engagements | Engagement type system (full tax enum) | ✅ Complete | ✅ Complete | ✅ Complete
10 | 2 - CRM Core | Engagements | IRS filing deadline + scheduler | ✅ Complete | ✅ Complete | ✅ Complete
11 | 2 - CRM Core | Engagements | Recurring engagement logic | ✅ Complete | N/A | ✅ Complete
12 | 2 - CRM Core | Tasks | Task assignment to staff | ✅ Complete | ✅ Complete | ✅ Complete
13 | 2 - CRM Core | Tasks | Staff workload view | ✅ Complete | N/A | ✅ Complete
14 | 2 - CRM Core | Client Intake | Client intake form | ✅ Complete | N/A | ✅ Complete
15 | 2 - CRM Core | Client Import | CSV client import | ✅ Complete | ❌ Wizard not built | 🔵 Partial
16 | 2 - CRM Core | Client Import | QuickBooks client import | ✅ Complete | ❌ Wizard not built | 🔵 Partial
17 | 3 - Document System | Storage | S3 storage adapter | ✅ Complete | N/A | ✅ Complete
18 | 3 - Document System | Documents | Document model + tax categories | ✅ Complete | ✅ Complete | ✅ Complete
19 | 3 - Document System | Documents | Document versioning | ✅ Complete | N/A | ✅ Complete
20 | 3 - Document System | Documents | Document access audit log | ✅ Complete | N/A | ✅ Complete
21 | 3 - Document System | Documents | Document search and filter | ✅ Complete | ✅ Complete | ✅ Complete
22 | 4 - Document Requests | Doc Requests | Document request model | ✅ Complete | ❌ Checklist UI not built | 🔵 Partial
23 | 4 - Document Requests | Doc Requests | Client portal upload flow | ✅ Complete | ✅ Complete | ✅ Complete
24 | 5 - E-Signatures | E-Signatures | Dropbox Sign integration | ✅ Complete | N/A | ✅ Complete
25 | 5 - E-Signatures | IRS Auth | IRS authorization (8821/2848) | ✅ Complete | ✅ Complete — Apr 21 | ✅ Complete
26 | 6 - Client Portal | Portal | Portal auth + session management | ✅ Complete | ❌ Login flow not built | 🔵 Partial
27 | 6 - Client Portal | Portal | Portal dashboard + to-do | ✅ Complete | ✅ Complete | ✅ Complete
28 | 6 - Client Portal | Portal | Portal documents tab | ✅ Complete | ✅ Complete | ✅ Complete
29 | 6 - Client Portal | Portal | Portal invoices + Stripe Elements | ✅ Complete | 🔵 Mock — Stripe Elements pending | 🔵 Partial
30 | 7 - Billing | Invoices | Invoice model + CRUD | ✅ Complete | ✅ Complete | ✅ Complete
31 | 7 - Billing | Extensions | Extension filing + tracking | ✅ Complete | ✅ Complete — Apr 21 | ✅ Complete
32 | 7 - Billing | Stripe | Stripe Connect billing | ✅ Complete | 🔵 Partial | 🔵 Partial
33 | 8 - Automations | Automations | Automation engine + presets | ✅ Complete | N/A | ✅ Complete
34 | 9 - Notifications | Notifications | Notification system | ✅ Complete | N/A | ✅ Complete
35 | 10 - Integrations | QuickBooks | QuickBooks OAuth + sync | ✅ Complete | N/A | ✅ Complete
36 | 10 - Integrations | Calendar | Google + Outlook Calendar | ✅ Complete | N/A | ✅ Complete
37 | 11 - Compliance | Security | Audit log + 2FA + data retention | ✅ Complete | N/A | ✅ Complete
38 | 11 - Compliance | Security | Security headers + CSP | ✅ Complete (prod only) | N/A | ✅ Complete
39 | 11 - Compliance | Compliance | IRS 4557 WISP | ✅ Complete | N/A — Manual doc pending | 🔵 Partial
40 | 11B - Notes | Notes | Internal notes on any entity | ✅ Complete | ✅ Complete | ✅ Complete
41 | 11C - Messaging | Messaging | Firm-to-client messaging | ✅ Complete | ✅ Complete | ✅ Complete
42 | 11D - Portal Preview | Portal | Staff portal preview endpoint | ✅ Complete | ✅ Complete — Apr 21 | ✅ Complete
43 | 11E - Firm Chat | Firm Chat | Internal team chat + channels | ✅ Complete | ✅ Complete | ✅ Complete
── PHASE 12 FRONTEND — See dedicated sheet for full detail ──
44 | 12 - Frontend | Foundation | Project scaffold, auth, app shell | N/A | ✅ Complete | ✅ Complete
45 | 12 - Frontend | Clients | Client list, cards, detail, new client | N/A | ✅ Complete | ✅ Complete
46 | 12 - Frontend | Clients | IRS Auth Badge + tab on client detail | N/A | ✅ Complete — Apr 21 | ✅ Complete
47 | 12 - Frontend | Clients | CSV + QuickBooks import wizard | N/A | ❌ Not built | ❌ Not Built
48 | 12 - Frontend | Engagements | Engagements list + detail + new form | N/A | ✅ Complete | ✅ Complete
49 | 12 - Frontend | Engagements | Extension filing UI | N/A | ✅ Complete — Apr 21 | ✅ Complete
50 | 12 - Frontend | Tasks | Tasks list + creation + detail | N/A | ✅ Complete | ✅ Complete
51 | 12 - Frontend | Documents | Document library | N/A | ✅ Complete | ✅ Complete
52 | 12 - Frontend | Documents | Document request checklist UI | N/A | ❌ Not built | ❌ Not Built
53 | 12 - Frontend | Billing | Invoices list + detail | N/A | ✅ Complete | ✅ Complete
54 | 12 - Frontend | Portal | Portal shell + tabs (To-do, Docs, Invoices, Messages) | N/A | ✅ Complete | ✅ Complete
55 | 12 - Frontend | Portal | Portal preview (staff view) | N/A | ✅ Complete — Apr 21 | ✅ Complete
56 | 12 - Frontend | Portal | Portal login flow (client-facing) | N/A | ❌ Not built | ❌ Not Built
57 | 12 - Frontend | Portal | Stripe Elements for Pay Now | N/A | ❌ Not built | ❌ Not Built
58 | 12 - Frontend | Dashboard | Priority work view + tax deadline watch | N/A | ✅ Complete | ✅ Complete
59 | 12 - Frontend | Firm Chat | Firm Chat page + channel list | N/A | ✅ Complete | ✅ Complete
60 | 12 - Frontend | Firm Chat | Message feed + compose + channel management | N/A | ❌ Not built | ❌ Not Built
61 | 12 - Frontend | Settings | Settings page (Profile, Firm, Team + Invite) | N/A | ✅ Complete — Apr 21 | ✅ Complete
62 | 12 - Frontend | Polish | Skeleton loading screens audit | N/A | ❌ Not built | ❌ Not Built
63 | 12 - Frontend | Polish | Full end-to-end integration pass | N/A | ❌ Not built | ❌ Not Built
64 | 12 - Frontend | Polish | Demo data seed script (realistic tax firm) | N/A | ❌ Not built | ❌ Not Built
── PRE-LAUNCH CHECKLIST (must complete before first real firm) ──
65 | Pre-Launch | Security | Password reset flow (no endpoints yet) | ❌ Not built | ❌ Not built | ❌ Not Built
66 | Pre-Launch | Security | Login rate limiting (slowapi on /auth/token) | ❌ Not built | N/A | ❌ Not Built
67 | Pre-Launch | Security | Staff refresh tokens | ❌ Not built | N/A | ❌ Not Built
68 | Pre-Launch | Security | CORS production config | ❌ Not built | N/A | ❌ Not Built
69 | Pre-Launch | Infrastructure | AWS SES domain verification + production access | ❌ Not built | N/A | ❌ Not Built
70 | Pre-Launch | Infrastructure | Stripe Connect full activation | ❌ Not built | N/A | ❌ Not Built
71 | Pre-Launch | Infrastructure | S3 production bucket hardening | ❌ Not built | N/A | ❌ Not Built
72 | Pre-Launch | Compliance | OWASP ZAP penetration test | ⚠️ Manual Task | N/A | ⚠️ Manual Task
73 | Pre-Launch | Compliance | IRS 4557 compliance documentation | ⚠️ Manual Task | N/A | ⚠️ Manual Task

## Phase 12 — Frontend
ID | Sub-Phase | Module | Page / Component | Key Frontend Task | Backend Dep | Status | Notes
12A — Foundation
12A-1 | 12A — Foundation | Setup | Project scaffold | Next.js 14+ App Router, TypeScript, Tailwind CSS, shadcn/ui, Inter font, globals.css | None | ✅ Complete
12A-2 | 12A — Foundation | Setup | Color system | Full JAMM PX color token system in tailwind.config.ts | None | ✅ Complete
12A-3 | 12A — Foundation | Layout | Sidebar component | Collapsible sidebar, nav order, Firm Chat badge, RBAC visibility | None | ✅ Complete
12A-4 | 12A — Foundation | Layout | App shell + dark mode | Root layout, dark/light mode toggle, verified both modes | JWT auth | ✅ Complete
12B — Clients
12B-1 | 12B — Clients | Clients | Client list page | Toolbar: search, card/row toggle, + New Client. Frontend filtering. | GET /clients | ✅ Complete
12B-2 | 12B — Clients | Clients | Card view | Client cards: name, engagement count, contact, status badges | GET /clients | ✅ Complete
12B-3 | 12B — Clients | Clients | Row view | Table rows with client name, contact, engagement count | GET /clients | ✅ Complete
12B-4 | 12B — Clients | Clients | Empty state | No clients empty state with + New Client CTA | None | ✅ Complete
12B-5 | 12B — Clients | Clients | New client modal | Name, industry, entity type, email, notes. Two-col grid. | POST /clients | ✅ Complete
12B-6 | 12B — Clients | Client detail | Client detail page | Breadcrumb, tabs: Overview, Engagements, Documents, Billing, IRS Auth, Messages | GET /clients/{id} | ✅ Complete | IRS Auth tab added Apr 21
12B-7 | 12B — Clients | IRS Auth | IRS Auth Badge + tab | Pill badge with status, hover tooltip, click→IRS Auth tab. Tab with send modal. | GET /irs-authorizations/check/{id} | ✅ Complete | Built Apr 21
12B-8 | 12B — Clients | Client Import | CSV + QB import wizard | Step-by-step import wizard for CSV and QuickBooks paths | POST /clients/import | ❌ Not Built
12C — Engagements & Tasks
12C-1 | 12C — Engagements | Engagements | Engagements list page | List with toolbar, filing deadline badge, extension badge | GET /engagements | ✅ Complete
12C-2 | 12C — Engagements | Engagements | Engagement detail page | Overview, Tasks, Documents tabs. Deadline badge. Extension panel. | GET /engagements/{id} | ✅ Complete | Extension panel rebuilt Apr 21
12C-3 | 12C — Engagements | Engagements | New engagement form | Full tax enum dropdown, auto-populates IRS deadline | POST /engagements | ✅ Complete
12C-4 | 12C — Engagements | Tasks | Tasks list page | Cross-client table, status filter, + New Task | GET /tasks | ✅ Complete
12C-5 | 12C — Engagements | Tasks | Task detail | Inline/slide-over: title, status, due date, assignee, notes | PATCH /tasks/{id} | ✅ Complete | Needs verification
12C-6 | 12C — Engagements | Extensions | Extension filing UI | Panel on engagement detail: file/update modal, deadline color logic, role gating | POST /extensions/file | ✅ Complete | Fully rebuilt Apr 21
12D — Documents
12D-1 | 12D — Documents | Documents | Document library page | Table with tax category badges, signed URL download | GET /documents | ✅ Complete
12D-2 | 12D — Documents | Documents | Document request UI | Checklist with upload status, progress bar, in engagement Documents tab | GET /document-requests/{id} | ❌ Not Built | Priority — demo critical
12D-3 | 12D — Documents | Documents | Empty states | Zero docs and zero doc request empty states | None | ✅ Complete
12E — Billing
12E-1 | 12E — Billing | Invoices | Invoices list page | Invoice table with status badges, amounts, due dates | GET /invoices | ✅ Complete
12E-2 | 12E — Billing | Invoices | Invoice detail | Invoice detail with line items, PDF download | GET /invoices/{id} | ✅ Complete
12E-3 | 12E — Billing | Invoices | New invoice form | Create invoice with line items, client select, send action | POST /invoices | ✅ Complete
12F — Client Portal
12F-1 | 12F — Portal | Portal | Portal layout shell | Top bar, tab row, no sidebar. Always #1F3148 top bar. | Portal JWT | ✅ Complete
12F-2 | 12F — Portal | Portal | To-do tab | Greeting, action cards, completed section at 0.7 opacity | GET /portal/dashboard | ✅ Complete
12F-3 | 12F — Portal | Portal | Documents tab | Client-visible documents with signed URL download | GET /portal/documents | ✅ Complete
12F-4 | 12F — Portal | Portal | Invoices tab + Pay Now | Invoice list, Pay Now button. Stripe Elements pending. | GET /portal/invoices | 🔵 Partial | Stripe Elements not wired
12F-5 | 12F — Portal | Portal | Dark/light mode | Portal defaults dark, light toggle in settings | None | ✅ Complete
12F-6 | 12F — Portal | Notes | Notes floating panel | Floating tab on all entity detail pages, slide-out panel, compose box | GET/POST /notes | ✅ Complete
12F-7 | 12F — Portal | Messaging | Messages tab (staff side) | Messages tab on client detail, thread view, compose box | GET/POST /messages | ✅ Complete
12F-8 | 12F — Portal | Messaging | Messages tab (portal side) | 4th portal tab, client perspective thread view | GET /portal/messages | ✅ Complete
12F-9 | 12F — Portal | Portal | Portal preview (staff view) | Single API call to /portal/preview/{id}. 4 tabs. Generated-at footer. | GET /portal/preview/{id} | ✅ Complete | Fully rebuilt Apr 21
12F-10 | 12F — Portal | Portal | Portal login flow (client-facing) | Client login page with firm slug, password, invite accept flow | POST /portal/auth/login | ❌ Not Built | Pre-launch required
12G — Dashboard & Polish
12G-1 | 12G — Dashboard | Dashboard | Priority work view | Cross-client feed: overdue, pending docs, deadline watch section | GET /dashboard/summary | ✅ Complete
12G-2 | 12G — Dashboard | Feedback | Toast notifications | Bottom-right stack, auto-dismiss, success/error/warning with Why? link | All mutations | ✅ Complete
12G-3 | 12G — Polish | Feedback | Skeleton loading screens audit | Audit all pages — replace spinners with skeletons | None | ❌ Not Built
12G-4 | 12G — Polish | Polish | Empty states audit | Audit all list pages for missing empty states | None | 🔵 Partial
12G-5 | 12G — Polish | Polish | Full end-to-end integration pass | Login → dashboard → client → engagement → task → doc → invoice → portal | All | ❌ Not Built
12G-6 | 12G — Polish | Polish | Demo data seed script | Realistic tax firm: 5 clients, engagements with IRS deadlines, extensions, auths | All models | ❌ Not Built | High priority for demo
12H — Firm Chat
12H-1 | 12H — Firm Chat | Firm Chat | Channel list + layout | Two-column layout, channel list, sidebar badge | GET /firm-chat/channels | ✅ Complete
12H-2 | 12H — Firm Chat | Firm Chat | Message feed + compose | Chronological feed, consecutive collapse, @mentions, file attachments | GET/POST /firm-chat/channels/{id}/messages | ❌ Not Built
12H-3 | 12H — Firm Chat | Firm Chat | Channel management | Create/rename/delete (firm_owner only), empty states | POST/PATCH/DELETE /firm-chat/channels | ❌ Not Built
12I — Settings
12I-1 | 12I — Settings | Settings | Settings page | Profile, Firm, Team tabs. Invite form. /users/firm endpoint added. | GET /users/firm, GET /users/, POST /users/ | ✅ Complete | Built Apr 21 — includes backend /users/firm endpoint

## Expansion Roadmap
Seq | Phase | Domain | Feature | Description | Strategic Reason | Status
🔴 IMMEDIATE POST-LAUNCH PRIORITY
1 | 13A - Tax Practice Features | IRS Integration | IRS transcript request workflow | TranscriptRequest model, check active 8821, retrieve from IRS e-Services, store in S3. Transcript panel on Client detail. | Tax firms pull transcripts on nearly every return. Eliminates manual IRS website login per client. | 🔵 Backend Complete — Frontend Pending
2 | 13A - Tax Practice Features | Client Portal | Tax organizer in client portal | TaxOrganizer model, section-by-section form in portal, staff reviews structured responses. Save progress, submit at end. | Replaces emailed PDF form. Structured digital collection. | 🔵 Backend Complete — Frontend Pending
Email integration — firms live in their inbox
3 | 13B - Email Integration | Email | Gmail OAuth integration | OAuth2 Gmail per firm, EmailThread model linking threads to engagement_id by client email. | Reduces context switching between inbox and JAMM PX. | ❌ Not Started
4 | 13B - Email Integration | Email | Email → engagement linking | Auto-match incoming emails to engagements by client email. Manual linking for unmatched. | Eliminates searching inbox for client context. | ❌ Not Started
5 | 13B - Email Integration | Email | Send emails from JAMM PX | Staff replies to client emails from engagement view via Gmail API. | Full audit trail on all client communication. | ❌ Not Started
Firm-wide visibility
6 | 14 - Advanced Dashboards | Dashboards | Firm KPI dashboard | Active engagements, completed this month, overdue, revenue collected vs invoiced, avg duration. | Firm owners make better decisions with this data. | ❌ Not Started
7 | 14 - Advanced Dashboards | Dashboards | Engagement health scoring | Score 1-100: days since activity, overdue tasks, doc completion %, staff login. Healthy/At Risk/Critical. | Proactively identify engagements about to miss deadlines. | ❌ Not Started
8 | 14 - Advanced Dashboards | Dashboards | Capacity planning view | Staff utilization, overload warnings >90%, drag-drop task reassignment. | Prevents staff burnout and missed deadlines. | ❌ Not Started
9 | 14 - Advanced Dashboards | Dashboards | IRS compliance deadline calendar | Firm-wide calendar of all filing deadlines. Color-coded. Export to Google/Outlook. | Tax-specific differentiator — no competitor surfaces this clearly at small-firm price. | ❌ Not Started
Smart alerts and suggestions
10 | 15 - Engagement Intelligence | Intelligence | Task bottleneck detection | Detect task In Progress > X days. Flag as bottleneck. Suggest reassignment. | Directly reduces missed deadlines — top firm pain point. | ❌ Not Started
11 | 15 - Engagement Intelligence | Intelligence | Document stagnation alerts | Detect doc request with no activity > 5 days. Auto-send client reminder option. | Automates chasing clients for documents. | ❌ Not Started
12 | 15 - Engagement Intelligence | Intelligence | Smart due date suggestions | Suggest task due date based on engagement due date, past task duration, staff workload. | Reduces cognitive load — faster data entry. | ❌ Not Started
13 | 15 - Engagement Intelligence | Intelligence | Next step recommendations | After key events (doc complete, e-sign, invoice paid), suggest next step. | Guides junior staff — reduces training time. | ❌ Not Started
Flexibility — let firms configure JAMM PX to their workflow
14 | 16 - Flexibility | Flexibility | Custom fields per entity | Custom fields on Client, Engagement, Contact. Stored as JSON. Searchable. | Different firms track different data. | ❌ Not Started
15 | 16 - Flexibility | Flexibility | Custom engagement types | Firm creates own types beyond built-in set. Configure auto-attach templates. | Advisory and niche service firms need custom types. | ❌ Not Started
16 | 16 - Flexibility | Flexibility | Firm terminology overrides | Allow firm to rename 'Engagement'→'Matter', 'Client'→'Customer' etc. | Reduces friction for firms from other software. | ❌ Not Started
17 | 16 - Flexibility | Flexibility | Custom notification templates | Firm customises email templates with merge fields. Rich text editor. | White-label feel — important for professional firms. | ❌ Not Started
Data-driven insights
18 | 17 - Analytics | Analytics | Revenue analytics | Monthly/quarterly: invoiced vs collected, AR aging, revenue by type/client. | Firm owners currently do this in spreadsheets. | ❌ Not Started
19 | 17 - Analytics | Analytics | Client responsiveness metrics | Avg time from doc request sent to response. Avg time to e-sign. | Helps firms set realistic timelines. | ❌ Not Started
20 | 17 - Analytics | Analytics | Automation time-saved estimation | Hours saved by automation: count × estimated manual time. | Powerful retention metric — firms quantify ROI. | ❌ Not Started
21 | 17 - Analytics | Analytics | Overdue heatmap | Visualise overdue tasks/engagements by staff, week, client. | Operations intelligence for firm owners. | ❌ Not Started
Templates — reduce repetitive setup work
22 | 18 - Templates | Templates | Engagement template library | Predefined engagement with tasks, doc checklist, letter template. | Most firms do same types repeatedly — templates eliminate re-setup. | ❌ Not Started
23 | 18 - Templates | Templates | Engagement cloning | Clone any engagement: tasks, doc checklist, notes. Same or different client. | Major time saver for annual recurring work. | ❌ Not Started
Deeper integrations
24 | 19 - Integrations | Integrations | Webhook sender (outbound) | Firm configures outbound webhooks for Zapier/Make.com. | Opens JAMM PX to entire Zapier ecosystem. | ❌ Not Started
25 | 19 - Integrations | Integrations | Xero integration | OAuth2 Xero as QB alternative for UK/Australia market. | Expands addressable market. | ❌ Not Started
Enterprise requirements
26 | 20 - Compliance | Compliance | SOC 2 Type II preparation | SOC 2 controls via Vanta or Drata. | Unlocks enterprise sales — firms >20 staff require SOC 2. | ❌ Not Started
27 | 20 - Compliance | Compliance | Cyber liability insurance | Obtain cyber liability insurance. | Required by enterprise procurement. | ❌ Not Started
28 | 20 - Compliance | Compliance | Legal policy upgrade | TOS, Privacy Policy, DPA via SaaS lawyer. | Enterprise clients require DPA before signing. | ❌ Not Started
Growth tools
29 | 21 - Growth | Growth | Referral tracking | Track referral source per client, referral network in analytics. | Accounting firms grow almost entirely by referral. | ❌ Not Started
30 | 21 - Growth | Growth | Client NPS tracking | Automated NPS after engagement completion. Flag detractors. | Systematic client satisfaction tracking. | ❌ Not Started
Build ONLY after product-market fit confirmed
31 | 22 - Mobile | Mobile | Client portal mobile app | React Native iOS + Android for portal only: docs, sign, pay, notifications. | Mobile doc upload removes biggest client friction. | ❌ Not Started