## AI Instructions
JAMM PX — AI INSTRUCTIONS SHEET
PRODUCT NAME — ALWAYS USE THIS
Product name: JAMM PX (short form) or JAMM Practice Experience (full form). NEVER use 'JAMM OS' — this name is retired.
CURRENT BUILD STATE — April 27 2026 — BUILD COMPLETE
Backend: ALL phases complete (Phases 1–11E). 415 passing, 11 failing (8 security headers + 3 pre-existing), 2 skipped. slowapi installed. @limiter.limit("5/minute") on /auth/token. Login brute-force protection active. Frontend (Phase 12): Complete — all mock data replaced with real API calls. Portal page, document detail, NewTaskModal all wired to live endpoints. Alembic: head at 7d35737819be. 30 migrations applied. 15 automation presets seeded (9 default-on, 6 default-off). Dev login: owner@jamm.com / password123 Test DB: accounting_test ¦ Demo DB: accounting_dev Recovery if tables missing: alembic stamp base → alembic upgrade head
SESSION 1 COMPLETE — April 22 2026
Built: Automations tab in Settings (frontend). 15 presets total (up from 8). Toggle UI with optimistic UI, section splitting, Default on badges. Key finding: No Radix UI packages installed — shadcn components that depend on Radix must be built natively. Auth pattern confirmed: const { user } = useAuth() from @/lib/hooks/useAuth. Role: user?.role. Toast: import { toast } from 'sonner'. Axios: import api from '@/lib/api'. All list endpoints return { items: [], total: N } — always use .then((r) => r.data?.items ?? r.data)
SESSION 2 COMPLETE — April 22 2026
2A: QBO AR Balance card on client detail Overview tab. GET /clients/{id}/qbo-ar. 15-min in-memory cache. 5s timeout. Silent fail on error/timeout. 2B: WIP Summary dashboard widget. GET /reports/wip. Joins time_entries→engagements→clients. 5-min staleTime. Empty state when no time entries. 2C: Client Health Indicator. GET /clients/{id}/health. Colored dot on client list + cards + detail page. Hover tooltip with reasons. AT RISK / NEEDS ATTENTION / HEALTHY. 10-min staleTime. Loads independently. Infra: Tests now use accounting_test. accounting_dev permanently protected. Infra: conftest.py uses checkfirst=True in create_all(). Infra: seed_dev_data.py created — 4 clients, 8 engagements, 16 tasks, 15 presets.
SESSION 3 COMPLETE — April 22 2026
3A: GET /dashboard/metrics built — MRR, AR, WIP, Overdue, Utilization, Deadlines, Unsigned Docs. All scoped to firm_id. manager_or_above required. 3B: dashboard/page.tsx fully wired — stat cards, WIP widget restored, deadline list, utilization bars, overdue table with mark-complete, signature table. Key finding: time_entries.user_id (not assigned_to), signature_envelopes.subject (not title), Engagement has no assigned_to. 374 passing, 0 TypeScript errors.
PRODUCT IDENTITY
JAMM PX pioneers the Practice Experience category — not practice management. Replaces 4-5 disconnected tools. Target: Firm owner or staff at a 2-10 person tax or advisory firm. Core promise: Automate entire client work cycle from engagement creation to invoice payment at flat per-firm price. Competitors: Karbon, TaxDome, Canopy, Financial Cents. We win on category, flat pricing, and tax-specific features.
PRICING MODEL
Starter: $99/mo, month-to-month, up to 2 staff Professional: $199/mo, month-to-month, unlimited staff Tax Firm: $299/mo, annual only, full product + white glove Founding member offer: First 25 firms get Professional at $199/mo locked for life.
DOMAIN LANGUAGE — NEVER SUBSTITUTE SYNONYMS
Firm = the accounting business that pays for and uses JAMM PX Client = the accounting firm's customer Engagement = a unit of billable work. NEVER call this a 'Project' Task = a discrete action item belonging to both a Client and an Engagement Document Request = a checklist sent to a client asking them to upload specific files Automation Rule = an if/then trigger that fires actions automatically Staff = employees of the firm who use JAMM PX internally Practice Experience = the category JAMM PX pioneers. Never use 'practice management'.
TECH STACK — NEVER DEVIATE WITHOUT EXPLICIT INSTRUCTION
Backend: FastAPI, PostgreSQL 14+, SQLAlchemy ORM 2.0 (Mapped[] syntax only), Pydantic v2, Alembic, Uvicorn + Gunicorn, Docker Frontend: Next.js 16 App Router, TypeScript, Tailwind CSS, shadcn/ui, Axios with JWT interceptor, TanStack Query Infrastructure: AWS S3 (signed URLs only, never public), AWS SES, Stripe Connect, Dropbox Sign for e-signatures
KEY ARCHITECTURE RULES
firm_id always server-side — never in Create schemas, always injected from JWT SQLAlchemy 2.0 select() style only — older query style is off-limits Background tasks must create their own SessionLocal() in try/finally — never inherit request session Enums with dots or special characters: use native_enum=False, store as VARCHAR Routers are thin — no business logic ever Signed URLs only for all file access — never public S3 URLs, 1 hour maximum expiry All list endpoints return { items: [], total: N } — always use .then((r) => r.data?.items ?? r.data) Migration procedure: verify current → generate → READ the file → apply → confirm. Never skip reading. QBO AR service has 5s timeout and silent fail — never raise to user bcrypt directly, never passlib — passlib broken with bcrypt >= 4.0 extra_metadata not metadata — metadata is reserved in SQLAlchemy Login endpoint is JSON body (LoginRequest), not OAuth2 form data weasyprint uses lazy import inside render function — GTK unavailable on Windows
DEV STARTUP
Backend: uvicorn app.main:app --reload --port 8000 (from project root) Frontend: npm run dev (from frontend/ folder — localhost:3000) Rebuild demo data: python seed_dev_data.py (from project root after any DB wipe) Run tests: pytest (uses accounting_test, never touches accounting_dev) Recovery if tables missing: alembic stamp base → alembic upgrade head
SESSION 4 COMPLETE — April 22 2026
4A Backend: Migration 0021_portal_magic_link_fields — added magic_link_token_hash (VARCHAR 64, unique) and magic_link_expires_at (TIMESTAMPTZ) to portal_sessions. Service: portal_magic_link.py — generate_magic_link() stores SHA-256 hash only, never raw token. exchange_magic_link() clears token after use (one-time use). POST /portal/magic-link (manager_or_above) + GET /portal/auth (public). Both in app/api/portal.py. 4B Frontend: Send Portal Link button on client detail Overview tab (firm_owner/manager only). /portal/auth/page.tsx — auto-exchanges token on mount, stores JWT, redirects to /portal. Portal login page updated with magic link section (currently shows toast — real endpoint deferred pending rate limiting). 378 passing, 0 TypeScript errors. Alembic: 0021_portal_magic_link_fields.
SESSIONS 8 + BEHAVIORAL LOG A COMPLETE — April 22 2026 Session 8: PortalInvoices.tsx fully wired to real API. @stripe/stripe-js + @stripe/react-stripe-js installed. Stripe Elements inline (CardNumber, Expiry, CVC). Pay Now → POST /portal/invoices/{id}/pay → client_secret → confirmCardPayment(). Optimistic status update + success toast on payment. Proxy fix: Next.js API route now forwards Authorization header for portal JWT calls. Toaster added to root layout.tsx. 0 TypeScript errors. Behavioral Log Session A: behavioral_events table created. Migration 0022_add_behavioral_events_table applied. log_event() utility in app/services/behavioral_log.py — fire-and-forget, own SessionLocal(), silently swallows all exceptions. Composite index ix_behavioral_events_firm_type_time on (firm_id, event_type, occurred_at). 4 tests passing. Full suite: 390 passing, 11 failing (pre-existing), 2 skipped. NEXT SESSION — Behavioral Log Session B: Drop log_event() calls into ALL service files across every domain (engagement, document, invoice, portal, task, IRS, firm chat, staff, onboarding). Full Section 5 event set from Master Product Vision. Purely additive — no migrations, no schema changes.
SESSION TONIGHT COMPLETE — April 27 2026 Item 1: datetime.utcnow() fixed in portal_preview_service.py. Item 2: Portal main page wired. GET /portal/me + GET /portal/documents added. PortalTodo fetches /portal/dashboard. PortalDocuments fetches /portal/documents. PortalMessages fetches /portal/clients/{id}/messages. Skeleton loading on all tabs. Auth errors redirect to /portal/login. Item 3: Document detail page wired — useFetch + documentsApi.get(). Skeleton loading. Download button calls documentsApi.getSignedUrl(). Item 4: NewTaskModal — clientsApi.list() + engagementsApi.list() replace mock data. Infra: slowapi was missing from venv (caused 87-test collapse). Now installed. Test count restored: 415 passing, 11 failing (pre-existing), 2 skipped. Note: password_reset_service.py and /auth/forgot-password + /auth/reset-password confirmed present in codebase — Pre-Launch checklist updated to ✅ Complete for this item.
FINAL BUILD SESSION — April 27 2026 Rate limit: @limiter.limit('5/minute') applied to /auth/token in app/api/auth.py. limiter and Request were already imported — one line added. 415 passing, 11 failing (pre-existing), 2 skipped. Build confirmed complete. ALL PRE-LAUNCH CODE WORK DONE. No more Claude Code until post-demo. Remaining pre-launch items are infrastructure (Andrew + buddy): AWS SES production access, S3 hardening, Stripe live mode, CORS prod config, staff refresh tokens, slug test fixes.
8A Wire PortalInvoices.tsx to real API (replace mock data). On Pay Now click: call POST /portal/invoices/{id}/pay → get Stripe payment intent client_secret. Render Stripe Elements inline: @stripe/stripe-js + @stripe/react-stripe-js. On payment success: optimistic invoice status update + success toast. Backend fully built — this is frontend wiring only.

## Execution Roadmap
JAMM PX — Execution Roadmap
Seq | Phase | Module | Feature | Backend Task | Frontend Task | Status
✅ Complete
1 | 1 - Multi-Tenancy | Rename | Project→Engagement rename | ✅ Complete | N/A | ✅ Complete
2 | 1 - Multi-Tenancy | Multi-Tenancy | Firm model | ✅ Complete | N/A | ✅ Complete
3 | 1 - Multi-Tenancy | Multi-Tenancy | firm_id on all models | ✅ Complete | N/A | ✅ Complete
4 | 1 - Multi-Tenancy | Multi-Tenancy | Tenant guard dependency | ✅ Complete | N/A | ✅ Complete
5 | 1 - Multi-Tenancy | Multi-Tenancy | Tenant isolation enforcement | ✅ Complete | N/A | ✅ Complete
6 | 1 - Multi-Tenancy | RBAC | Role model + permissions | ✅ Complete | N/A | ✅ Complete
7 | 1 - Multi-Tenancy | RBAC | Session invalidation on role change | ✅ Complete | N/A | ✅ Complete
8 | 2 - CRM Core | Engagements | Engagement model + tax deadlines | ✅ Complete | ✅ Complete | ✅ Complete
9 | 2 - CRM Core | Engagements | Engagement type system (full tax enum) | ✅ Complete | ✅ Complete | ✅ Complete
10 | 2 - CRM Core | Engagements | IRS filing deadline + scheduler | ✅ Complete | ✅ Complete | ✅ Complete
11 | 2 - CRM Core | Engagements | Recurring engagement logic | ✅ Complete | N/A | ✅ Complete
12 | 2 - CRM Core | Tasks | Task assignment to staff | ✅ Complete | ✅ Complete | ✅ Complete
13 | 2 - CRM Core | Tasks | Staff workload view | ✅ Complete | N/A | ✅ Complete
14 | 2 - CRM Core | Client Intake | Client intake form | ✅ Complete | N/A | ✅ Complete
15 | 2 - CRM Core | Client Import | CSV client import | ✅ Complete | ❌ Not Started | 🔵 In Progress
16 | 2 - CRM Core | Client Import | QuickBooks client import | ✅ Complete | ❌ Not Started | 🔵 In Progress
17 | 3 - Document System | Storage | S3 storage adapter | ✅ Complete | N/A | ✅ Complete
18 | 3 - Document System | Documents | Document model + tax categories | ✅ Complete | ✅ Complete | ✅ Complete
19 | 3 - Document System | Documents | Document versioning | ✅ Complete | N/A | ✅ Complete
20 | 3 - Document System | Documents | Document access audit log | ✅ Complete | N/A | ✅ Complete
21 | 3 - Document System | Documents | Document search and filter | ✅ Complete | ✅ Complete | ✅ Complete
22 | 4 - Doc Requests | Doc Requests | Document request model | ✅ Complete | ✅ Complete | ✅ Complete
23 | 4 - Doc Requests | Doc Requests | Client portal upload flow | ✅ Complete | ✅ Complete | ✅ Complete
24 | 5 - E-Signatures | E-Signatures | Dropbox Sign integration | ✅ Complete | N/A | ✅ Complete
25 | 5 - E-Signatures | IRS Auth | IRS authorization (8821/2848) | ✅ Complete | ✅ Complete | ✅ Complete
26 | 6 - Client Portal | Portal | Portal auth + session management | ✅ Complete | ✅ Complete | ✅ Complete
27 | 6 - Client Portal | Portal | Portal dashboard + to-do | ✅ Complete | ✅ Complete | ✅ Complete
28 | 6 - Client Portal | Portal | Portal documents tab | ✅ Complete | ✅ Complete | ✅ Complete
29 | 6 - Client Portal | Portal | Portal invoices + Stripe Elements | ✅ Complete | ✅ Complete | ✅ Complete
30 | 7 - Billing | Invoices | Invoice model + CRUD | ✅ Complete | ✅ Complete | ✅ Complete
31 | 7 - Billing | Extensions | Extension filing + tracking | ✅ Complete | ✅ Complete | ✅ Complete
32 | 7 - Billing | Stripe | Stripe Connect billing | ✅ Complete | 🔵 In Progress | 🔵 In Progress
33 | 8 - Automations | Automations | Automation engine + 15 presets | ✅ Complete | ✅ Complete | ✅ Complete
34 | 9 - Notifications | Notifications | Notification system | ✅ Complete | N/A | ✅ Complete
35 | 10 - Integrations | QuickBooks | QuickBooks OAuth + sync | ✅ Complete | N/A | ✅ Complete
36 | 10 - Integrations | Calendar | Google + Outlook Calendar | ✅ Complete | N/A | ✅ Complete
37 | 11 - Compliance | Security | Audit log + 2FA + data retention | ✅ Complete | N/A | ✅ Complete
38 | 11 - Compliance | Security | Security headers + CSP | ✅ Complete | N/A | ✅ Complete
39 | 11 - Compliance | Compliance | IRS 4557 WISP | ✅ Complete | 🔵 In Progress | 🔵 In Progress
40 | 11B - Notes | Notes | Internal notes on any entity | ✅ Complete | ✅ Complete | ✅ Complete
41 | 11C - Messaging | Messaging | Firm-to-client messaging | ✅ Complete | ✅ Complete | ✅ Complete
42 | 11D - Portal Preview | Portal | Staff portal preview endpoint | ✅ Complete | ✅ Complete | ✅ Complete
43 | 11E - Firm Chat | Firm Chat | Internal team chat + channels | ✅ Complete | ✅ Complete | ✅ Complete
── PHASE 12 FRONTEND — See dedicated sheet for full detail ──
44 | 12 - Frontend | Foundation | Project scaffold, auth, app shell | N/A | ✅ Complete | ✅ Complete
45 | 12 - Frontend | Clients | Client list, cards, detail, new client | N/A | ✅ Complete | ✅ Complete
46 | 12 - Frontend | Clients | IRS Auth Badge + tab on client detail | N/A | ✅ Complete | ✅ Complete
47 | 12 - Frontend | Clients | CSV + QuickBooks import wizard | N/A | ❌ Not Started | ❌ Not Started
❌ Not Started
✅ Complete
S1 | Session 1 | Automations | 15 preset automation rules in backend | ✅ Complete | N/A | ✅ Complete
S1 | Session 1 | Automations | Automations tab in Settings — toggle UI, section splitting, Default on badges | N/A | ✅ Complete | ✅ Complete
✅ Complete
S2 | Session 2 | QBO AR | QBO AR balance on client profile | GET /clients/{id}/qbo-ar — QBO Reports API, 15-min cache, 5s timeout | Card on client detail Overview tab — green/amber balance, loading skeleton | ✅ Complete
S2 | Session 2 | WIP | WIP summary dashboard widget | GET /reports/wip — unbilled time entries aggregated by engagement, sorted by value | Dashboard widget — total value, top 5 engagements, empty state | ✅ Complete
S2 | Session 2 | Health | Client health indicator on client list | GET /clients/{id}/health — AT RISK / NEEDS ATTENTION / HEALTHY computed from existing data | Colored dot left of name on list + cards + detail header. Hover tooltip with reasons. | ✅ Complete
S2 | Session 2 | Infra | Test DB separation | accounting_test for pytest, accounting_dev for dev app. checkfirst=True in conftest. | seed_dev_data.py — 4 clients, 8 engagements, 16 tasks, 15 presets | ✅ Complete
✅ Complete
S3 | Session 3 | Analytics | 7-metric analytics dashboard | GET /dashboard/metrics — MRR, AR, WIP, overdue, utilization, deadlines, unsigned docs | Dashboard page wired to real data — 4 stat cards, deadline list, utilization bars, overdue list | ✅ Complete
✅ Complete
S4 | Session 4 | Portal | Magic-link client portal access | 2 fields on portal_sessions, POST /portal/magic-link, GET /portal/auth?token=. SHA-256 hashed, one-time use. | Send Portal Link button on client detail, /portal/auth page, magic link option on login | ✅ Complete
✅ Complete
S5 | Session 5 | WIP | Dedicated WIP Report page | Already built in Session 2B | Full table grouped by client/engagement, CSV export. Lives in Billing section. | ✅ Complete
S5 | Session 5 | Bulk Actions | Bulk actions for tasks, engagements, invoices | PATCH /tasks/bulk, /engagements/bulk, /invoices/bulk — all enforce firm_id isolation | Checkbox column, floating action bar, bulk action options per entity type | ✅ Complete
S5 | Session 5 | Calendar | 6-month deadline calendar | GET /engagements/calendar?days=180 — both deadlines, annotated with type/client/status | Month grid + list view, color-coded by status, dashboard compact widget | ✅ Complete
⬜ Planned
S8 | Session 8 | Payments | Wire portal Pay Now to Stripe Elements | Backend fully built — POST /portal/invoices/{id}/pay + webhook handler | PortalInvoices.tsx → real API → Stripe Elements inline → success toast | ✅ Complete
❌ Not Started
PL | ✅ Complete | Security | Password reset endpoints | ✅ Complete | None | ✅ Complete
PL | ✅ Complete | Security | Login rate limiting | slowapi on /auth/token — brute-force protection | None | ✅ Complete
PL | ❌ Not Started | Intelligence | Behavioral Event Log table | ✅ Complete | None | ❌ Not Started
PL | ❌ Not Started | Security | Client-initiated magic link — rate limiting + user enumeration protection | slowapi rate limit per email on new /portal/request-link endpoint. Consistent response regardless of email existence. | Wire "Send me a link" button on portal login page (currently shows toast). Requires backend endpoint first. | ❌ Not Started

## Phase 12 — Frontend
JAMM PX — Phase 12 Frontend Build Tracker
ID | Sub-Phase | Module | Page / Component | Key Frontend Task | Backend Dep | Status | Notes
12A — Foundation
12A-1 | 12A — Foundation | Setup | Project scaffold | Next.js 16 App Router, TypeScript, Tailwind CSS, shadcn/ui, Inter font, globals.css | None | ✅ Complete
12A-2 | 12A — Foundation | Setup | Color system | Full JAMM PX color token system in tailwind.config.ts | None | ✅ Complete
12A-3 | 12A — Foundation | Layout | Sidebar component | Collapsible sidebar, nav order, Firm Chat badge, RBAC visibility | None | ✅ Complete
12A-4 | 12A — Foundation | Layout | App shell + dark mode | Root layout, dark/light mode toggle, verified both modes | JWT auth | ✅ Complete
12B — Clients
12B-1 | 12B — Clients | Clients | Client list page | Toolbar: search, card/row toggle, + New Client. Frontend filtering. | GET /clients | ✅ Complete
12B-2 | 12B — Clients | Clients | Card view | Client cards: name, engagement count, contact, status badges | GET /clients | ✅ Complete
12B-3 | 12B — Clients | Clients | Row view | Table rows with client name, contact, engagement count | GET /clients | ✅ Complete
12B-4 | 12B — Clients | Clients | Empty state | No clients empty state with + New Client CTA | None | ✅ Complete
12B-5 | 12B — Clients | Clients | New client modal | Name, industry, entity type, email, notes. Two-col grid. | POST /clients | ✅ Complete
12B-6 | 12B — Clients | Client detail | Client detail page | Breadcrumb, tabs: Overview, Engagements, Documents, Billing, IRS Auth, Messages | GET /clients/{id} | ✅ Complete | IRS Auth tab added Apr 21
12B-7 | 12B — Clients | IRS Auth | IRS Auth Badge + tab | Pill badge with status, hover tooltip, click→IRS Auth tab. Tab with send modal. | GET /irs-authorizations/check/{id} | ✅ Complete | Built Apr 21
12B-8 | 12B — Clients | Client detail | QBO AR Balance card | Card on Overview tab — green/amber balance, last payment, loading skeleton, not-connected state | GET /clients/{id}/qbo-ar | ✅ Complete | Built Session 2A
12B-9 | 12B — Clients | Client detail | Health Indicator dot | Colored 8px dot + showLabel in header. Hover tooltip with reasons. Loads independently. | GET /clients/{id}/health | ✅ Complete | Built Session 2C
12B-10 | 12B — Clients | Client Import | CSV + QB import wizard | Step-by-step import wizard for CSV and QuickBooks paths | POST /clients/import | ❌ Not Started | ❌ Not Started
12C — Engagements & Tasks
12C-1 | 12C — Engagements | Engagements | Engagements list page | List with toolbar, filing deadline badge, extension badge | GET /engagements | ✅ Complete
12C-2 | 12C — Engagements | Engagements | Engagement detail page | Overview, Tasks, Documents tabs. Deadline badge. Extension panel. | GET /engagements/{id} | ✅ Complete | Extension panel rebuilt Apr 21
12C-3 | 12C — Engagements | Engagements | New engagement form | Full tax enum dropdown, auto-populates IRS deadline | POST /engagements | ✅ Complete
12C-4 | 12C — Engagements | Tasks | Tasks list page | Cross-client table, status filter, + New Task | GET /tasks | ✅ Complete
12C-5 | 12C — Engagements | Tasks | Task detail | Inline/slide-over: title, status, due date, assignee, notes | PATCH /tasks/{id} | ✅ Complete | Verified Apr 21
12C-6 | 12C — Engagements | Extensions | Extension filing UI | Panel on engagement detail: file/update modal, deadline color logic, role gating | POST /extensions/file | ✅ Complete | Fully rebuilt Apr 21
12D — Documents
12D-1 | 12D — Documents | Documents | Document library page | Table with tax category badges, signed URL download | GET /documents | ✅ Complete
12D-2 | 12D — Documents | Documents | Document request UI | Checklist with upload status, progress bar, in engagement Documents tab | GET /document-requests/{id} | ✅ Complete | Built Apr 21
12D-3 | 12D — Documents | Documents | Empty states | Zero docs and zero doc request empty states | None | ✅ Complete
12E — Billing
12E-1 | 12E — Billing | Invoices | Invoices list page | Invoice table with status badges, amounts, due dates | GET /invoices | ✅ Complete
12E-2 | 12E — Billing | Invoices | Invoice detail | Invoice detail with line items, PDF download | GET /invoices/{id} | ✅ Complete
12E-3 | 12E — Billing | Invoices | New invoice form | Create invoice with line items, client select, send action | POST /invoices | ✅ Complete
12F — Client Portal
12F-1 | 12F — Portal | Portal | Portal layout shell | Top bar, tab row, no sidebar. Always #1F3148 top bar. | Portal JWT | ✅ Complete
12F-2 | 12F — Portal | Portal | To-do tab | ✅ Complete | GET /portal/dashboard | ✅ Complete
12F-3 | 12F — Portal | Portal | Documents tab | Client-visible documents with signed URL download | GET /portal/documents | ✅ Complete
12F-4 | 12F — Portal | Portal | Invoices tab + Pay Now | ✅ Complete | GET /portal/invoices | ✅ Complete | ✅ Complete — Stripe Elements fully wired. PortalInvoices.tsx live.
12F-5 | 12F — Portal | Portal | Dark/light mode | Portal defaults dark, light toggle in settings | None | ✅ Complete
12F-6 | 12F — Portal | Notes | Notes floating panel | Floating tab on all entity detail pages, slide-out panel, compose box | GET/POST /notes | ✅ Complete
12F-7 | 12F — Portal | Messaging | Messages tab (staff side) | Messages tab on client detail, thread view, compose box | GET/POST /messages | ✅ Complete
12F-8 | 12F — Portal | Messaging | Messages tab (portal side) | 4th portal tab, client perspective thread view | GET /portal/messages | ✅ Complete
12F-9 | 12F — Portal | Portal | Portal preview (staff view) | Single API call to /portal/preview/{id}. 4 tabs. Generated-at footer. | GET /portal/preview/{id} | ✅ Complete | Fully rebuilt Apr 21
12F-10 | 12F — Portal | Portal | Portal login flow (client-facing) | Client login page with email/password, magic link option. /portal/login/page.tsx and /portal/auth/page.tsx both built and wired. | POST /portal/auth/login | ✅ Complete | ✅ Complete
12G — Dashboard & Polish
12G-1 | 12G — Dashboard | Dashboard | Priority work view | ✅ Complete | GET /dashboard/summary | ✅ Complete
12G-2 | 12G — Dashboard | Dashboard | WIP Summary widget | Total WIP value, top 5 engagements by unbilled value, empty state | GET /reports/wip | ✅ Complete | Built Session 2B
12G-3 | 12G — Dashboard | Feedback | Toast notifications | Bottom-right stack, auto-dismiss, success/error/warning with Why? link | All mutations | ✅ Complete
12G-4 | 12G — Polish | Feedback | Skeleton loading screens audit | Audit all pages — replace spinners with skeletons | None | ❌ Not Started
12G-5 | 12G — Polish | Polish | Empty states audit | Audit all list pages for missing empty states | None | 🔵 In Progress
12G-6 | 12G — Polish | Polish | Full end-to-end integration pass | Login → dashboard → client → engagement → task → doc → invoice → portal | All | 🔵 In Progress | 🔵 In Progress
12G-7 | 12G — Polish | Polish | Demo data seed script | seed_dev_data.py — 4 clients, 8 engagements, 16 tasks, 15 presets | All models | ✅ Complete | Built Session 2 infra
12H — Firm Chat
12H-1 | 12H — Firm Chat | Firm Chat | Firm Chat full UI | Two-column layout, channel list, message feed, compose box, @mentions, sidebar badge | GET/POST /firm-chat/channels | ✅ Complete
12I — Settings
12I-1 | 12I — Settings | Settings | Automations tab | ✅ Complete | GET/POST /automation-rules | ✅ Complete | Built Apr 22 — 15 presets, 9 default-on
12I-2 | 12I — Settings | Settings | Client health indicator dots | HealthDot component on ClientTable + ClientCard + client detail header | GET /clients/{id}/health | ✅ Complete | Built Session 2C

## Automation Presets
JAMM PX — Automation Presets (15 Total — Seeded Apr 22 2026)
Name | Description | Trigger Event | Default State | Status
Default ON — 9 presets active when firm is created
Document Request Reminder (3-day) | Sends a reminder to the client 3 days after a document request is created if still pending | doc_request.created | ON | ✅ Complete
E-Signature Reminder (2-day) | Sends a reminder to the client 2 days after an engagement letter is sent if not yet signed | esign.sent | ON | ✅ Complete
Overdue Task Alert to Staff | Notifies the assigned staff member when a task becomes overdue | task.assigned | ON | ✅ Complete
New Client Welcome Email | Sends a welcome email to the client when they are first added to the system | client.created | ON | ✅ Complete
Invoice Overdue Reminder | Sends a payment reminder to the client when an invoice becomes overdue | invoice.overdue | ON | ✅ Complete
Extension Filed Auto-Notify | Notifies client of extension, creates deadline task, and updates engagement status | extension.filed | ON | ✅ Complete
IRS Authorization Expiry Warning | Alerts staff and client when an IRS authorization is approaching expiry | irs_authorization.expiry_approaching | ON | ✅ Complete
Invoice Overdue Escalating Sequence | Sends escalating payment reminders on day 1, day 7, and notifies firm owner on day 14 | invoice.overdue | ON | ✅ Complete
Engagement Deadline Approaching — 14-day Alert | Notifies assigned staff 14 days before an engagement deadline | engagement.deadline_approaching | ON | ✅ Complete
Default OFF — 6 presets available to activate in Settings → Automations
Auto-Create Invoice on Engagement Completion | Automatically creates an invoice when an engagement is marked complete | engagement.completed | OFF | ⬜ Available
Notify Staff When Documents Are Complete | Notifies assigned staff when all items in a document request are uploaded | doc_request.completed | OFF | ⬜ Available
Recurring Engagement Kickoff Notification | Sends notification when a recurring engagement is auto-created | engagement.recurrence_created | OFF | ⬜ Available
1040 Season Kickoff | Sends welcome email and creates intake tasks when a 1040 engagement is opened | engagement.created | OFF | ⬜ Available
Return Completed: Client Delivery Loop | Creates delivery task, generates invoice, and notifies client when a return is complete | engagement.completed | OFF | ⬜ Available
New Client Full Onboarding Sequence | Sends welcome email, creates onboarding tasks, and sends intake document request for new clients | client.created | OFF | ⬜ Available

## Expansion Roadmap
JAMM PX — Expansion Roadmap (Post-Revenue Features)
Seq | Phase | Domain | Feature | Description | Strategic Reason | Status
🔴 IMMEDIATE POST-LAUNCH PRIORITY
1 | 13A - Tax Practice | IRS Integration | IRS transcript request workflow | TranscriptRequest model, check active 8821, retrieve from IRS e-Services, store in S3. Transcript panel on Client detail. | Tax firms pull transcripts on nearly every return. Eliminates manual IRS website login per client. | ✅ Complete
2 | 13A - Tax Practice | Client Portal | Tax organizer in client portal | TaxOrganizer model, section-by-section form in portal, staff reviews structured responses. | Replaces emailed PDF form. Structured digital collection. | ✅ Complete
Email integration
3 | 13B - Email | Email | Gmail OAuth integration | OAuth2 Gmail per firm, EmailThread model linking threads to engagement_id by client email. | Reduces context switching between inbox and JAMM PX. | ❌ Not Started
4 | 13B - Email | Email | Email → engagement linking | Auto-match incoming emails to engagements by client email. Manual linking for unmatched. | Eliminates searching inbox for client context. | ❌ Not Started
5 | 13B - Email | Email | Send emails from JAMM PX | Staff replies to client emails from engagement view via Gmail API. | Full audit trail on all client communication. | ❌ Not Started
Firm-wide visibility
6 | 14 - Dashboards | Dashboards | Firm KPI dashboard | ✅ Complete | Firm owners make better decisions with this data. | ❌ Not Started
7 | 14 - Dashboards | Dashboards | Engagement health scoring | Score 1-100: days since activity, overdue tasks, doc completion %, staff login. | Proactively identify engagements about to miss deadlines. | ❌ Not Started
8 | 14 - Dashboards | Dashboards | Capacity planning view | Staff utilization, overload warnings >90%, drag-drop task reassignment. | Prevents staff burnout and missed deadlines. | ❌ Not Started
9 | 14 - Dashboards | Dashboards | IRS compliance deadline calendar | Firm-wide calendar of all filing deadlines. Color-coded. Export to Google/Outlook. | Tax-specific differentiator — no competitor surfaces this at small-firm price. | ❌ Not Started
Smart alerts and suggestions
10 | 15 - Intelligence | Intelligence | Task bottleneck detection | 🔵 In Progress | Directly reduces missed deadlines — top firm pain point. | ❌ Not Started
11 | 15 - Intelligence | Intelligence | Document stagnation alerts | Detect doc request with no activity > 5 days. Auto-send client reminder option. | Automates chasing clients for documents. | ❌ Not Started
12 | 15 - Intelligence | Intelligence | Smart due date suggestions | Suggest task due date based on engagement due date, past task duration, staff workload. | Reduces cognitive load — faster data entry. | ❌ Not Started
13 | 15 - Intelligence | Intelligence | Next step recommendations | ✅ Complete | Guides junior staff — reduces training time. | ❌ Not Started
Flexibility
14 | 16 - Flexibility | Flexibility | Custom fields per entity | Custom fields on Client, Engagement, Contact. Stored as JSON. Searchable. | Different firms track different data. | ❌ Not Started
15 | 16 - Flexibility | Flexibility | Custom engagement types | Firm creates own types beyond built-in set. Configure auto-attach templates. | Advisory and niche service firms need custom types. | ❌ Not Started
16 | 16 - Flexibility | Flexibility | Firm terminology overrides | Allow firm to rename 'Engagement'→'Matter', 'Client'→'Customer' etc. | Reduces friction for firms from other software. | ❌ Not Started
17 | 16 - Flexibility | Flexibility | Custom notification templates | Firm customises email templates with merge fields. Rich text editor. | White-label feel — important for professional firms. | ❌ Not Started
Analytics
18 | 17 - Analytics | Analytics | Revenue analytics | Monthly/quarterly: invoiced vs collected, AR aging, revenue by type/client. | Firm owners currently do this in spreadsheets. | ❌ Not Started
19 | 17 - Analytics | Analytics | Client responsiveness metrics | Avg time from doc request sent to response. Avg time to e-sign. | Helps firms set realistic timelines. | ❌ Not Started
20 | 17 - Analytics | Analytics | Automation time-saved estimation | Hours saved by automation: count × estimated manual time. | Powerful retention metric — firms quantify ROI. | ❌ Not Started
21 | 17 - Analytics | Analytics | Overdue heatmap | Visualise overdue tasks/engagements by staff, week, client. | Operations intelligence for firm owners. | ❌ Not Started
Templates
22 | 18 - Templates | Templates | Engagement template library | Predefined engagement with tasks, doc checklist, letter template. | Most firms do same types repeatedly — templates eliminate re-setup. | ❌ Not Started
23 | 18 - Templates | Templates | Engagement cloning | Clone any engagement: tasks, doc checklist, notes. Same or different client. | Major time saver for annual recurring work. | ❌ Not Started
Deeper integrations
24 | 19 - Integrations | Integrations | Webhook sender (outbound) | Firm configures outbound webhooks for Zapier/Make.com. | Opens JAMM PX to entire Zapier ecosystem. | ❌ Not Started
25 | 19 - Integrations | Integrations | Xero integration | OAuth2 Xero as QB alternative for UK/Australia market. | Expands addressable market. | ❌ Not Started
Enterprise requirements
26 | 20 - Compliance | Compliance | SOC 2 Type II preparation | SOC 2 controls via Vanta or Drata. | Unlocks enterprise sales — firms >20 staff require SOC 2. | ❌ Not Started
27 | 20 - Compliance | Compliance | Cyber liability insurance | Obtain cyber liability insurance. | Required by enterprise procurement. | ❌ Not Started
28 | 20 - Compliance | Compliance | Legal policy upgrade | TOS, Privacy Policy, DPA via SaaS lawyer. | Enterprise clients require DPA before signing. | ❌ Not Started
Growth tools
29 | 21 - Growth | Growth | Referral tracking | Track referral source per client, referral network in analytics. | Accounting firms grow almost entirely by referral. | ❌ Not Started
30 | 21 - Growth | Growth | Client NPS tracking | Automated NPS after engagement completion. Flag detractors. | Systematic client satisfaction tracking. | ❌ Not Started
Build ONLY after product-market fit confirmed
31 | 22 - Mobile | Mobile | Client portal mobile app | React Native iOS + Android for portal only: docs, sign, pay, notifications. | Mobile doc upload removes biggest client friction. | ❌ Not Started

## Build Status
JAMM PX — Session Build Status
As of April 27, 2026 ¦ 415 passing, 11 failing (pre-existing), 2 skipped ¦ Alembic: 7d35737819be (head)
Session | Feature | Type | Status | Files Changed | Test Impact | Alembic | Notes
Backend Phases 1–11 | Full backend — multitenancy, CRM, docs, e-sign, portal, billing, automation, notifications, QBO, compliance | Backend | ✅ Complete | 231 files | 373 passing at handoff | 0020 (head) | IRS 4557 WISP. Argon2. JWT. Stripe Connect. Dropbox Sign.
Phase 12 | Full frontend — all pages, design system, light+dark, notes, messaging, firm chat, portal preview | Frontend | ✅ Complete | 80+ files | No backend tests | unchanged | shadcn/ui. TanStack Query. Axios interceptor.
Session 1 | Automations tab — 15 presets, toggle UI, Settings, seed scripts | Frontend + Seed | ✅ Complete | 3 files + scripts | +2 tests fixed | unchanged | 9 default-on. 6 default-off. seed_firm_presets().
Session 2 Infra | Test DB separation, conftest checkfirst, QBO timeout fix, seed_dev_data.py | Infrastructure | ✅ Complete | 3 files | Stable 370/11 | unchanged | accounting_dev permanently protected from pytest wipes.
Session 2A | QBO AR Balance card on client detail Overview tab | Backend + Frontend | ✅ Complete | 5 files | No new tests | unchanged | GET /clients/{id}/qbo-ar. 15-min cache. 5s timeout. Silent fail.
Session 2B | WIP Summary dashboard widget | Backend + Frontend | ✅ Complete | 5 files | No new tests | unchanged | GET /reports/wip. 5-min staleTime. Empty state when no time entries.
Session 2C | Client Health Indicator — dot + tooltip on client list and detail | Backend + Frontend | ✅ Complete | 7 files | No new tests | unchanged | GET /clients/{id}/health. 10-min staleTime. Loads independently.
Session 3 | Firm Analytics Dashboard — 7-metric endpoint + dashboard wired | Backend + Frontend | ✅ Complete | 6 files | +4 tests (374 total) | unchanged | GET /dashboard/metrics. MRR, AR, WIP, Overdue, Utilization, Deadlines, Unsigned.
Session 4 | Magic-link client portal access | Backend + Frontend | ✅ Complete | ~5 files | +4 tests (378 total) | 0021 — 2 fields added | POST /portal/magic-link. GET /portal/auth?token=. SHA-256. One-time use.
Session 5A | WIP Report page — full table, CSV export | Frontend | ✅ Complete | ~2 files | None | unchanged | Extends Session 2B. Lives in Billing section.
Session 5B | Bulk actions — tasks, engagements, invoices | Backend + Frontend | ✅ Complete | ~8 files | +6 tests | unchanged | PATCH /tasks/bulk etc. Floating action bar.
Session 5C | 6-month deadline calendar | Backend + Frontend | ✅ Complete | ~4 files | +2 tests | unchanged | GET /engagements/calendar?days=180. Month grid + list view.
Session 8 | Wire portal Pay Now to Stripe Elements | Frontend | ✅ Complete | ~3 files | None — frontend only | unchanged | @stripe/stripe-js + @stripe/react-stripe-js installed. Proxy fix: Authorization header forwarded for portal JWT. Toaster added to root layout. Inline Stripe Elements wired.
Behavioral Event Log | JAMM Index intelligence network event log table | Backend | ✅ Complete | ~4 files | +4 tests (390 total) | 0022 — behavioral_events table | behavioral_events table. log_event() utility. fire-and-forget, own SessionLocal(). Composite index on (firm_id, event_type, occurred_at). Session B: drop log_event() calls into all service files — full Section 5 event set.
Behavioral Log Session B | Drop log_event() calls into all service files — full Section 5 event set from Master Product Vision | Backend | 🔵 In Progress | ~15-20 service files | None expected | unchanged | Purely additive. No migrations. No schema changes. Engagement, document, invoice, portal, task, IRS, firm chat, staff ops, onboarding/lifecycle domains. All events from Section 5 of Master Product Vision.
April 27 Session | Mock data removal (portal page, doc detail, NewTaskModal), datetime fix, /portal/me + /portal/documents endpoints, slowapi install | Backend + Frontend | ✅ Complete | 5 backend files, 5 frontend files | +25 tests recovered | unchanged | 415 passing. All mock data removed from active pages. Portal fully wired to real API.
April 27 — Rate Limit | @limiter.limit('5/minute') decorator applied to /auth/token login endpoint | Backend | ✅ Complete | 1 file (app/api/auth.py) | 415 passing — no change | unchanged | One-line change. limiter and Request already imported. Brute-force protection now active on login.
❌ Not Started | Staff refresh tokens, CORS prod config, AWS SES, S3 hardening, Stripe live mode | Backend + Infra | ❌ Not Started | ~6 files | ~5 tests expected | maybe | slowapi. AWS SES domain verification. CORS origins.
🔵 In Progress | Language audit, animations, morning briefing card, skeleton audit | Frontend | POLISH | ~10 files | None | unchanged | ✅ Complete

## Pre-Launch Checklist
❌ Not Started
Area | Item | Priority | Status | Owner | Notes
Security | Password reset endpoints (POST /auth/forgot-password, POST /auth/reset-password) | CRITICAL | ✅ Complete | Claude Code | ✅ Complete — POST /auth/forgot-password and POST /auth/reset-password both exist in app/api/auth.py. password_reset_service.py built. Requires AWS SES to be live before usable in production.
Security | Login rate limiting on /auth/token using slowapi | HIGH | ✅ Complete | Claude Code | ✅ Complete — @limiter.limit("5/minute") decorator applied to /auth/token login endpoint in app/api/auth.py. Request object already present. 415 passing confirmed after change.
Security | Client-initiated magic link — rate limiting + user enumeration prevention | HIGH | ❌ Not Started | Claude Code | Portal login "Send me a link" button is currently a stub toast. Before wiring: (1) slowapi rate limit per email on new POST /portal/request-link endpoint, (2) consistent response regardless of whether email exists (prevents user enumeration). Both required before going live.
Security | Staff-side refresh tokens (portal has them, staff JWTs do not) | MEDIUM | ❌ Not Started | Claude Code | Flagged as Next.js API proxy layer TODO.
Security | CORS production configuration — update BACKEND_CORS_ORIGINS | HIGH | ❌ Not Started | Andrew | Must be set to production domain before go-live.
Security | Fix 3 stale test failures — slug collision in auth tests + notifications FK | LOW | ❌ Not Started | Claude Code | Replace hardcoded slugs with uuid4() generated values.
Infrastructure | AWS SES domain verification and production access request | HIGH | ❌ Not Started | Andrew | Sandbox only sends to verified emails. Production access needed.
Infrastructure | S3 production bucket hardening — bucket policy, versioning, encryption | HIGH | ❌ Not Started | Andrew | Dev bucket may have permissive settings. Audit before launch.
Infrastructure | Stripe Connect full activation (remove test mode) | HIGH | ❌ Not Started | Andrew | Live mode requires Stripe account verification.
Infrastructure | Behavioral Event Log table — required before first firm joins | CRITICAL | ✅ Complete | Claude Code | ✅ Complete — behavioral_events table, log_event() utility, 31 call sites across 14 service files across all service domains. Session B complete.
Frontend | Portal client-facing login flow | HIGH | ✅ Complete | Claude Code | ✅ Complete
Frontend | CSV + QuickBooks import wizard | MEDIUM | ❌ Not Started | Claude Code | ❌ Not Started
Testing | End-to-end testing with both servers running simultaneously | HIGH | ❌ Not Started | Andrew + Claude Code | Full flows: client → engagement → doc request → invoice → portal payment.
Testing | QBO AR card slow load — confirm 5s timeout resolves in production | LOW | 🔵 In Progress | Andrew | 🔵 In Progress
Testing | Security header tests — wire middleware for production HTTPS | LOW | ❌ Not Started | Claude Code | 8 tests fail in dev mode intentionally. Will pass behind HTTPS.
Demo Prep | Demo call with former employer — feedback session | HIGH | ❌ Not Started | Andrew | Use questions from Strategy doc Session 6D. Founding firm #1.
Demo Prep | Seed realistic demo data for demo call | MEDIUM | 🔵 In Progress | Andrew | seed_dev_data.py exists. May need richer data for demo.
Go-to-Market | Finalize product name — update all UI references from JAMM OS to JAMM PX | HIGH | 🔵 In Progress | Andrew | Some UI may still say JAMM OS.
Go-to-Market | Build pricing page with savings calculator | MEDIUM | ❌ Not Started | Claude Code | See Strategy doc Session 7D for copy framework.
Go-to-Market | Cold outreach list — small CPA and bookkeeping firms | MEDIUM | ❌ Not Started | Andrew | ⬜ Planned

## Session 8 — Next Steps
✅ Complete
Goal: Wire the Pay Now button in the client portal to real Stripe Elements. Backend fully built. This is frontend wiring only (~1-2 days).
Part | Task | Endpoint / File | Detail | Notes
8A Frontend | Wire PortalInvoices.tsx to real API | frontend/src/app/portal/invoices/page.tsx (or PortalInvoices.tsx — check filename) | Replace mock data import with call to GET /portal/invoices using portal JWT. Map response to Invoice type. | Backend endpoint already built: POST /portal/invoices/{id}/pay returns Stripe payment intent client_secret.
8A Frontend | POST /portal/magic-link | app/api/portal.py | Staff-only. Input: client_id from JWT, expiry_hours default 48. Generate secrets.token_hex(32). Store SHA-256 hash. Email raw token to client: /portal/auth?token={raw}. Return { sent: true, expires_at }. | Never store raw token. Only hash stored in DB. Raw token only in email URL.
8A Frontend | GET /portal/auth?token= | app/api/portal.py | Public endpoint. Hash incoming token SHA-256. Look up portal_session WHERE hash matches AND expiry > now. Found: issue portal JWT, clear magic_link fields (one-time use), return JWT. Not found/expired: 401. | Clear fields after use — prevents replay attacks.
8A Frontend | Tests | tests/test_magic_link.py (new) | test_magic_link_sends (201), test_magic_link_auth_success (200 + JWT returned), test_magic_link_expired (401), test_magic_link_one_time_use (second call returns 401) | ~4 tests. Check tenant isolation: staff cannot generate link for another firm client.
4B Frontend | Send Portal Link button | frontend/src/app/clients/[id]/page.tsx | Button on client detail Overview tab. Calls POST /portal/magic-link. Success toast: Portal link sent to {email} — expires in 48 hours. Disable if client has no email. | firm_owner and manager only — staff should not see this button.
4B Frontend | Portal auth page | frontend/src/app/portal/auth/page.tsx (new) | Reads ?token= from URL. Calls GET /portal/auth?token=. Stores JWT. Redirects to /portal. Show spinner during exchange. On error: clear message + link back. | This is the landing page from the magic link email.
4B Frontend | Magic link on portal login | frontend/src/app/portal/login/page.tsx | Keep existing email/password login. Add: Or get a magic link — enter email. Client-initiated request. Lower priority than staff-initiated flow. | Optional for launch. Staff-initiated Send Portal Link is the core feature.

## Key Decisions & Rules
JAMM PX — Key Architecture Decisions & Permanent Rules
Category | Rule / Decision | Why It Exists | Established
Database | Tests use accounting_test. Dev app uses accounting_dev. NEVER share. | pytest drop_all() was wiping dev data after every test run. | Session 2
Database | seed_dev_data.py is the canonical way to rebuild demo data after a wipe | Run from project root. Creates 4 clients, 8 engagements, 16 tasks, 15 presets. | Session 2
Database | conftest.py uses checkfirst=True in create_all() | Prevents INTERNALERROR when indexes already exist in accounting_test. | Session 2
Database | alembic stamp base → alembic upgrade head is the recovery procedure for stamp mismatch | Alembic can think DB is at head while tables don't exist. | Phase 11
Backend | Background tasks must create their own SessionLocal() in try/finally | Never inherit the request session in background tasks. | Phase 9
Backend | Enums with dots/special chars: native_enum=False, stored as VARCHAR | PostgreSQL native enums break on values with dots. | Phase 8
Backend | firm_id always injected from JWT, never from request body | Prevents cross-tenant data leaks. | Phase 1
Backend | SQLAlchemy 2.0 select() style only — never legacy query style | Consistency and future compatibility. | Phase 1
Backend | bcrypt directly, never passlib — passlib broken with bcrypt >= 4.0 | passlib's bcrypt backend incompatible with current bcrypt. | Phase 2
Backend | extra_metadata not metadata — metadata is reserved in SQLAlchemy | SQLAlchemy uses metadata internally on all model classes. | Phase 4
Backend | Login endpoint is JSON body (LoginRequest), not OAuth2 form data | Required to support totp_code and backup_code fields. | Phase 11
Backend | weasyprint uses lazy import inside render function — not top-level | GTK libraries unavailable on Windows locally. | Phase 7
Backend | QBO AR service: 5s timeout, specific Timeout exception, silent fail | External API calls must not block page renders. Fail gracefully. | Session 2
Backend | Two separate audit log models: DocumentAuditLog and AuditLog — never conflate | document_audit_logs and audit_logs are different tables for different purposes. | Phase 11
Frontend | Design system tokens: bg-brand / dark:bg-brand-btn for buttons | Consistent brand color across light and dark mode. | Phase 12
Frontend | Task.md workflow: always select all → delete → paste fresh, never append | Stale content causes duplicate blocks and errors in Claude Code. | Phase 12
Frontend | All list endpoints return { items: [], total: N } | Always use .then((r) => r.data?.items ?? r.data) in frontend calls. | Phase 12
Security | API keys: only in .env/.env.docker, GitHub secrets, production env vars | Never in chat, cloud storage, or documents. | Phase 10
Security | Signed URLs only for file access — 1 hour max expiry, never public S3 | IRS 4557 WISP compliance requirement. | Phase 3
Security | Audit logging on every sensitive action | Compliance requirement. Two models exist — see above. | Phase 11
Migration | Procedure: current → generate → READ the file → apply → confirm | Never skip reading the generated file before applying. | Phase 1
Migration | Both .env and .env.docker must be kept in sync for all API keys | Docker compose uses .env.docker, local dev uses .env. | Phase 10
Naming | Product: JAMM PX or JAMM Practice Experience. Never JAMM OS. | Category positioning: Practice Experience not practice management. | April 2026
Naming | Engagement (never Project), Staff, Client, Firm, Document Request, Automation Rule | Consistent vocabulary throughout UI and codebase. | Phase 1